## Central Line
Unit No. | DATE | Status | Number of cars affected by graffiti/shadows on this unit | Total Number of Tags found | Total Tags Removed / Cleaned | Total Tags Not Cleaned on this Unit | Car Number (s) of Tags not cleaned (shadows) | Date of 2nd visit to clean remaining tags | Number of tags removed | Date of 3rd visit to clean remaining tags | Number of tags removed2 | Train Inspected and Fit for service (Y/N) | Inspected by Supervisor/Manager (Name) | Date of Completing all shadows (Tags) on this Unit excluding acid etched shadows | Car Number (s) of Tags not cleaned due to acid etched shadows
91001 | 28/04/2025 |  | 1 | 1 | 1 | 0 | 0 |  | 0 |  | 0 | Y | D Mihalache | 28/04/2025
91003 | 30/06/2025 |  | 1 | 44 | 44 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 30/06/2025 |  | Total Trains | Total Units | Units Completed | % Completed
91005 | 09/06/2025 |  | 2 | 115 | 115 | 0 | 0 |  | 0 |  | 0 | Y | M. Ebietsuwa | 09/06/2025 |  | 85 | =COUNTA(A:A)1 | =COUNTA(N:N)1 | #VALUE!
91007
91009
91011 | 28/05/2025 |  | 2 | 250 | 250 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 28/05/2025
91013
91015 | 13/05/2025 |  | 2 | 98 | 98 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 13/05/2025 | 91015
91017
91019 | 19/06/2025 |  | 2 | 240 | 240 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 19/06/2025
91021 | 16/06/2025 |  | 2 | 200 | 200 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 16/06/2025
91023 | 07/05/2025 |  | 2 | 70 | 70 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 07/05/2025
91025
91027 | 12/06/2025 |  | 2 | 226 | 226 | 0 | 0 |  | 0 |  | 0 | Y | M. Ebietsuwa | 12/06/2025
91029
91031 | 25/05/2025 |  | 2 | 200 | 200 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 25/05/2025
91033 | 12/05/2025 |  | 2 | 120 | 120 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 12/05/2025 | 91033
91035
91037 | 15/04/2025 |  | 2 | 62 | 62 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 15/04/2025
91039 | 27/04/2025 |  | 2 | 49 | 49 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 27/04/2025
91041
91043
91045 | 08/07/2025 |  | 2 | 210 | 210 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 08/07/2025
91047
91049 | 19/05/2025 |  | 2 | 98 | 98 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 19/05/2025
91051 | 29/04/2025 |  | 2 | 2 | 2 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 29/04/2025
91053
91055 | 09/05/2025 |  | 2 | 216 | 216 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 09/06/2025
91057
91059
91061 | 20/05/2025 |  | 2 | 225 | 225 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 20/05/2025
91063 | 12/05/2025 |  | 2 | 108 | 108 | 0 | 0 |  | 0 |  | 0 | Y | M. Ebietsuwa | 12/05/2025 | 91063/92063
91065 | 28/04/2025 |  | 2 | 36 | 36 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 28/04/2025 | 91065/92065
91067
91069
91071
91073
91075
91077
91079
91081
91083 | 22/04/2025 |  | 2 | 200 | 200 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 22/04/2025 | 91083/92083
91085
91087
91089 | 24/04/2025 |  | 2 | 63 | 63 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 24/04/2025 | 91089/92089
91091 | 26/05/2025 |  | 2 | 102 | 102 | 0 | 0 |  | 0 |  | 0 | Y | M. Ebietsuwa | 26/05/2025
91093 | 28/04/2025 |  | 1 | 1 | 1 | 0 | 0 |  | 0 |  | 0 | Y | D Mihalache | 28/04/2025
91095 | 18/05/2025 |  | 2 | 119 | 119 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 18/05/2025
91097 | 04/05/2025 |  | 2 | 26 | 26 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 04/05/2025
91099 | 29/05/2025 |  | 2 | 4 | 4 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 29/05/2025
91101
91103
91105 | 14/04/2025 |  | 2 | 22 | 22 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 14/04/2025
91107
91109 | 28/04/2025 |  | 1 | 1 | 1 | 0 | 0 |  | 0 |  | 0 | Y | D Mihalache | 28/04/2025
91111
91113 | 28/04/2025 |  | 2 | 10 | 10 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 28/04/2025
91115
91117
91119
91121 | 29/05/2025 |  | 2 | 4 | 4 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 29/05/2025
91123
91125 | 01/06/2025 |  | 2 | 100 | 100 | 0 | 0 |  | 0 |  | 0 | Y | M. Ebietsuwa | 01/06/2025
91127 | 18/06/2025 |  | 2 | 290 | 290 | 0 | 0 |  | 0 |  | 0 | Y | E. Nyarko | 18/06/2025
91129 | 11/05/2025 |  | 2 | 80 | 80 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 11/05/2025 | 91129/92129
91131 | 25/05/2025 |  | 2 | 109 | 109 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 25/05/2025
91133 | 09/07/2025 |  | 2 | 260 | 260 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 09/07/2025
91135 | 01/06/2025 |  | 2 | 130 | 130 | 0 | 0 |  | 0 |  | 0 | Y | M. Ebietsuwa | 01/06/2025
91137
91139 | 29/05/2025 |  | 2 | 225 | 225 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 29/05/2025
91141 | 28/04/2025 |  | 2 | 6 | 6 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 28/04/2025
91143
91145 | 2025-06-08 |  | 2 | 230 | 230 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-06-08
91147
91149
91151 | 2025-05-04 |  | 2 | 33 | 33 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-05-04
91153 | 2025-05-18 |  | 2 | 95 | 95 | 0 | 0 |  | 0 |  | 0 | Y | M. Ebietsuwa | 2025-05-18
91155
91157
91159 | 2025-07-03 |  | 2 | 87 | 87 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-07-03
91161
91163 | 2025-04-28 |  | 2 | 4 | 4 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-04-28
91165 | 2025-05-08 |  | 2 | 82 | 82 | 0 | 0 |  | 0 |  | 0 | Y | L Dwyer | 2025-05-08
91167 | 2025-05-06 |  | 2 | 38 | 38 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-05-06 | 91167/92167
91169 | 2025-05-01 |  | 2 | 44 | 44 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-05-01
91171
91173 | 2025-05-14 |  | 2 | 200 | 200 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-05-14
91175 | 2025-05-05 |  | 2 | 42 | 42 | 0 | 0 |  | 0 |  | 0 | Y | M. Ebietsuwa | 2025-05-05
91177 | 2025-04-28 |  | 2 | 3 | 3 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-04-28 | 91177
91179 | 2025-05-27 |  | 2 | 225 | 225 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-05-27
91181
91183
91185 | 2025-05-01 |  | 2 | 32 | 32 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-05-01
91187
91189 | 2025-06-19 |  | 2 | 210 | 210 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-06-19
91191
91193 | 2025-05-05 |  | 2 | 48 | 48 | 0 | 0 |  | 0 |  | 0 | Y | M. Ebietsuwa | 2025-05-05
91195 | 2025-05-26 |  | 2 | 59 | 59 | 0 | 0 |  | 0 |  | 0 | Y | M. Ebietsuwa | 2025-05-26
91197 | 2025-04-29 |  | 2 | 16 | 16 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-04-29
91199 | 2025-05-21 |  | 2 | 200 | 200 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-05-21
91201 | 2025-04-28 |  | 1 | 1 | 1 | 0 | 0 |  | 0 |  | 0 | Y | D Mihalache | 2025-04-28
91203
91205 | 2025-05-21 |  | 2 | 208 | 208 | 0 | 0 |  | 0 |  | 0 | Y | C. Ebietsuwa | 2025-05-21
91207 | 2025-06-29 |  | 2 | 160 | 160 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-06-29
91209
91211 | 2025-04-30 |  | 2 | 28 | 28 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-04-30
91213 | 2025-06-04 |  | 1 | 20 | 20 | 0 | 0 |  | 0 |  | 0 | Y | E. Nyarko | 2025-06-04
91215
91217
91219
91221 | 2025-04-30 |  | 2 | 38 | 38 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-04-30
91223 | 2025-06-15 |  | 2 | 100 | 100 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-06-15
91225 | 2025-04-22 |  | 2 | 34 | 34 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-04-22 | 91225/92225
91227 | 2025-05-29 |  | 2 | 200 | 200 | 0 | 0 |  | 0 |  | 0 | Y | M. Ebietsuwa | 2025-05-29
91229
91231 | 2025-05-15 |  | 2 | 114 | 114 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-05-15
91233 | 2025-05-07 |  | 2 | 69 | 69 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-05-07 | 91233/92233
91235 | 2025-05-14 |  | 2 | 150 | 150 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-05-14
91237 | 2025-07-01 |  | 2 | 66 | 66 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-07-01
91239
91241
91243
91245
91247 | 2025-06-02 |  | 2 | 150 | 150 | 0 | 0 |  | 0 |  | 0 | Y | M. Ebietsuwa | 2025-06-02
91249 | 2025-05-13 |  | 2 | 76 | 76 | 0 | 0 |  | 0 |  | 0 | Y | M. Ebietsuwa | 2025-05-13
91251 | 2025-06-02 |  | 0 | 44 | 44 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-06-02
91253 | 2025-06-02 |  | 0 | 150 | 150 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-06-02
91255 | 2025-04-23 |  | 2 | 42 | 42 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-04-23 | 91255/92255
91257 | 2025-06-04 |  | 2 | 200 | 200 | 0 | 0 |  | 0 |  | 0 | Y | E. Nyarko | 2025-06-04
91259 | 2025-04-30 |  | 2 | 44 | 44 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-04-30
91261 | 2025-05-28 |  | 2 | 256 | 256 | 0 | 0 |  | 0 |  | 0 | Y | M. Ebietsuwa | 2025-05-28
91263
91265
91267 | 2025-05-12 |  | 2 | 79 | 79 | 0 | 0 |  | 0 |  | 0 | Y | M. Ebietsuwa | 2025-05-12 | 91267
91269 | 2025-07-01 |  | 2 | 133 | 133 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-07-01
91271 | 2025-06-05 |  | 2 | 248 | 248 | 0 | 0 |  | 0 |  | 0 | Y | M. Ebietsuwa | 2025-06-05
91273 | 2025-06-04 |  | 2 | 100 | 100 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-06-04
91275 | 2025-05-27 |  | 2 | 188 | 188 | 0 | 0 |  | 0 |  | 0 | Y | M. Ebietsuwa | 2025-05-27 | 91275
91277 | 2025-04-17 |  | 2 | 88 | 88 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-04-17 | 91277
91279 | 2025-06-01 |  | 2 | 114 | 114 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-06-01
91281 | 2025-05-28 |  | 1 | 21 | 21 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-05-28
91283 | 2025-05-25 |  | 2 | 200 | 200 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-05-25
91285 | 2025-05-04 |  | 2 | 42 | 42 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-05-04 | 91285/92285
91287 | 2025-04-21 |  | 2 | 52 | 52 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-04-21 | 91287
91289
91291
91293 | 2025-05-13 |  | 2 | 110 | 110 | 0 | 0 |  | 0 |  | 0 | Y | M. Ebietsuwa | 2025-05-13
91295 | 2025-05-03 |  | 2 | 130 | 130 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-06-03
91297
91299 | 2025-06-12 |  | 2 | 220 | 220 | 0 | 0 |  | 0 |  | 0 | Y | M. Ebietsuwa | 2025-06-12
91301
91303 | 2025-04-16 |  | 2 | 76 | 76 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-04-16
91305 | 2025-07-07 |  | 2 | 112 | 112 | 0 | 0 |  | 0 |  | 0 | Y | M. Ebietsuwa | 2025-07-07
91307 | 2025-05-28 |  | 1 | 3 | 3 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-05-28
91309 | 2025-05-11 |  | 2 | 82 | 82 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-05-11 | 91309/92309
91311 | 2025-05-27 |  | 2 | 202 | 202 | 0 | 0 |  | 0 |  | 0 | Y | M. Ebietsuwa | 2025-05-27
91313
91315 | 2025-06-08 |  | 2 | 220 | 220 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-06-08
91317 | 2025-05-07 |  | 2 | 77 | 77 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-05-07 | 91317/92317
91319
91321 | 2025-06-04 |  | 2 | 230 | 230 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-06-04
91323
91325 | 2025-05-22 |  | 2 | 200 | 200 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-05-22
91327
91329
91331
91333 | 2025-05-08 |  | 2 | 80 | 80 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-05-08 | 91333/92333
91335 | 2025-05-19 |  | 2 | 136 | 136 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-05-19 | 91335
91337
91339
91341
91343
91345 | 2025-06-08 |  | 2 | 64 | 64 | 0 | 0 |  | 0 |  | 0 | Y | M. Ebietsuwa | 2025-06-08
91347
91349 | 2025-05-26 |  | 2 | 98 | 98 | 0 | 0 |  | 0 |  | 0 | Y | M. Ebietsuwa | 2025-05-26
93002 | 2025-05-27 |  | 2 | 196 | 196 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-05-27
93004
93006 | 2025-05-13 |  | 2 | 56 | 56 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-05-13
93008
93010
93012
93014 | 2025-06-08 |  | 2 | 350 | 350 | 0 | 0 |  | 0 |  | 0 | Y | M. Ebietsuwa | 2025-06-08
93016 | 2025-05-28 |  | 1 | 7 | 7 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-05-28
93018
93020
93022
93024
93026 | 2025-04-28 |  | 1 | 1 | 1 | 0 | 0 |  | 0 |  | 0 | Y | D Mihalache | 2025-04-28
93028
93030
93032
93034
93036 | 2025-04-20 |  | 2 | 44 | 44 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-04-20
93038 | 2025-06-24 |  | 2 | 100 | 100 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-06-24
93040 | 2025-07-07 |  | 2 | 146 | 146 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-07-07
93042 | 2025-06-29 |  | 1 | 140 | 140 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-06-29
93044
93046 | 2025-06-30 |  | 2 | 212 | 212 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-06-30
93048 | 2025-04-13 |  | 2 | 40 | 40 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-04-13
93050 | 2025-05-15 |  | 2 | 124 | 124 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-05-15
93052
93054 | 2025-04-28 |  | 1 | 1 | 1 | 0 | 0 |  | 0 |  | 0 | Y | D Mihalache | 2025-04-28
93056
93058 | 2025-05-11 |  | 2 | 76 | 76 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-05-11 | 91058
93060
93062 | 2025-05-04 |  | 2 | 28 | 28 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-05-04
93064 | 2025-06-09 |  | 2 | 232 | 232 | 0 | 0 |  | 0 |  | 0 | Y | M. Ebietsuwa | 2025-06-09
93066
93068
93070
93072
93074 | 2025-04-15 |  | 2 | 38 | 38 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-04-15 | 93074
93076 | 2025-04-27 |  | 2 | 30 | 30 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-04-27
93078 | 2025-05-28 |  | 2 | 210 | 210 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-05-28
93080 | 2025-05-28 |  | 2 | 150 | 150 | 0 | 0 |  | 0 |  | 0 | Y | M. Ebietsuwa | 2025-05-28
93082
93084 | 2025-04-29 |  | 2 | 22 | 22 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-04-29
93086 | 2025-05-11 |  | 2 | 69 | 69 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-05-11
93088 | 2025-04-29 |  | 2 | 66 | 66 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-04-29
93090 | 2025-06-17 |  | 2 | 106 | 106 | 0 | 0 |  | 0 |  | 0 | Y | E. Nyarko | 2025-06-17
93092 | 2025-06-05 |  | 2 | 256 | 256 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-06-05
93094
93096 | 2025-05-29 |  | 2 | 4 | 4 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-05-29
93098
93100
93102 | 2025-06-09 |  | 2 | 200 | 200 | 0 | 0 |  | 0 |  | 0 | Y | M. Ebietsuwa | 2025-06-09
93104 | 2025-06-23 |  | 1 | 70 | 70 | 0 | 0 | 2025-06-29 | 60 |  | 0 | Y | E. Nyarko | 2025-06-23
93106
93108 | 2025-04-14 |  | 2 | 34 | 34 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-04-14
93110
93112 | 2025-04-28 |  | 2 | 32 | 32 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-04-28
93114 | 2025-05-21 |  | 2 | 202 | 202 | 0 | 0 |  | 0 |  | 0 | Y | C. Ebietsuwa | 2025-05-21
93116 | 2025-05-21 |  | 2 | 212 | 212 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-05-21
93118 | 2025-06-01 |  | 2 | 108 | 108 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-06-01
93120 | 2025-06-26 |  | 2 | 200 | 200 | 0 | 0 |  | 0 |  | 0 | Y | M. Ebietsuwa | 2025-06-26
93122
93124
93126
93128 | 2025-04-24 |  | 2 | 48 | 48 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-04-24 | 92128
93130 | 2025-06-18 |  | 2 | 270 | 270 | 0 | 0 |  | 0 |  | 0 | Y | E. Nyarko | 2025-06-18
93132 | 2025-04-27 |  | 2 | 36 | 36 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-04-27
93134 | 2025-06-23 |  | 2 | 100 | 100 | 0 | 0 |  | 0 |  | 0 | Y | E. Nyarko | 2025-06-23
93136
93138 | 2025-06-25 |  | 2 | 110 | 110 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-06-25
93140 | 2025-05-18 |  | 2 | 103 | 103 | 0 | 0 |  | 0 |  | 0 | Y | M. Ebietsuwa | 2025-05-18
93142
93144 | 2025-07-08 |  | 2 | 248 | 248 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-07-08
93146 | 2025-05-12 |  | 2 | 68 | 68 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-05-12
93148
93150 | 2025-06-17 |  | 2 | 130 | 130 | 0 | 0 |  | 0 |  | 0 | Y | E. Nyarko | 2025-06-17
93152 | 2025-06-04 |  | 2 | 250 | 250 | 0 | 0 |  | 0 |  | 0 | Y | E. Nyarko | 2025-06-04
93154
93156 | 2025-05-29 |  | 2 | 12 | 12 | 0 | 0 |  | 0 |  | 0 | Y | M. Ebietsuwa | 2025-05-29
93158
93160 | 2025-05-19 |  | 2 | 102 | 102 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-05-19 | 92160
93162
93164 | 2025-04-28 |  | 2 | 30 | 30 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-04-28 | 92164/93164
93166
93168
93170
93172
93174 | 2025-05-19 |  | 2 | 121 | 121 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-05-19
93176 | 2025-04-28 |  | 1 | 1 | 1 | 0 | 0 |  | 0 |  | 0 | Y | D Mihalache | 2025-04-28
93178 | 2025-05-29 |  | 2 | 12 | 12 | 0 | 0 |  | 0 |  | 0 | Y | M. Ebietsuwa | 2025-05-29
93180 | 2025-05-29 |  | 2 | 146 | 146 | 0 | 0 |  | 0 |  | 0 | Y | M. Ebietsuwa | 2025-05-29
93182
93184 | 2025-06-02 |  | 2 | 150 | 150 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-06-02
93186 | 2025-06-05 |  | 2 | 252 | 252 | 0 | 0 |  | 0 |  | 0 | Y | M. Ebietsuwa | 2025-06-05
93188
93190 | 2025-04-20 |  | 2 | 33 | 33 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-04-20
93192
93194 | 2025-05-11 |  | 2 | 88 | 88 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-05-11
93196 | 2025-05-08 |  | 2 | 76 | 76 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-05-08
93198 | 2025-05-01 |  | 2 | 48 | 48 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-05-01
93200 | 2025-07-03 |  | 2 | 99 | 99 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-07-03
93202
93204 | 2025-06-05 |  | 2 | 252 | 252 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-06-05
93206 | 2025-04-28 |  | 1 | 1 | 1 | 0 | 0 |  | 0 |  | 0 | Y | D Mihalache | 2025-04-28
93208
93210
93212
93214 | 2025-04-23 |  | 2 | 34 | 34 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-04-23 | 93214/92214
93216
93218 | 2025-06-03 |  | 2 | 130 | 130 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-06-03
93220
93222
93224
93226
93228 | 2025-06-12 |  | 2 | 204 | 204 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-06-12
93230 | 2025-04-30 |  | 2 | 40 | 40 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-04-30 | 92230/93230
93232
93234
93236
93238 | 2025-05-26 |  | 2 | 188 | 188 | 0 | 0 |  | 0 |  | 0 | Y
93240 | [12 empty] | M. Ebietsuwa | 2025-05-26
93242
93244
93246 | 2025-05-06 |  | 2 | 40 | 40 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-05-06
93248
93250 | 2025-06-15 |  | 2 | 112 | 112 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-06-15
93252 | 2025-07-02 |  | 2 | 88 | 88 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-07-02
93254
93256 | 2025-05-07 |  | 2 | 82 | 82 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-05-07 | 92256/93256
93258
93260 | 2025-06-16 |  | 2 | 220 | 220 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-06-16
93262
93264
93266
93402 | 2025-06-02 |  | 2 | 150 | 150 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-06-02
93404
93406 | 2025-05-22 |  | 2 | 150 | 150 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-05-22
93408 | 2025-04-14 |  | 2 | 24 | 24 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-04-14
93410 | 2025-05-11 |  | 2 | 98 | 98 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-05-11 | 93410
93412
93414 | 2025-05-18 |  | 2 | 94 | 94 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-05-18
93416 | 2025-06-29 |  | 1 | 120 | 120 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-06-29
93418
93420 | 2025-05-28 |  | 2 | 24 | 24 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-05-28
93422 | 2025-04-22 |  | 2 | 38 | 38 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-04-22 | 92422/93422
93424 | 2025-06-01 |  | 2 | 90 | 90 | 0 | 0 |  | 0 |  | 0 | Y | M. Ebietsuwa | 2025-06-01
93426
93428 | 2025-05-05 |  | 2 | 33 | 33 | 0 | 0 |  | 0 |  | 0 | Y | M. Ebietsuwa | 2025-05-05
93430 | 2025-05-22 |  | 2 | 206 | 206 | 0 | 0 |  | 0 |  | 0 | Y | C. Ebietsuwa | 2025-05-22
93432 | 2025-05-02 |  | 2 | 84 | 84 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-06-02
93434 | 2025-04-28 |  | 2 | 2 | 2 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-04-28
93436 | 2025-05-25 |  | 2 | 15 | 15 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-05-25
93438 | 2025-04-21 |  | 2 | 25 | 25 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-04-21 | 92438/93438
93440 | 2025-06-01 |  | 2 | 110 | 110 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-06-01
93442 | 2025-06-10 |  | 2 | 430 | 430 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-06-10
93444 | 2025-06-02 |  | 2 | 156 | 156 | 0 | 0 |  | 0 |  | 0 | Y | M. Ebietsuwa | 2025-06-02
93446
93448 | 2025-07-06 |  | 2 | 228 | 228 | 0 | 0 |  | 0 |  | 0 | Y | M. Ebietsuwa | 2025-07-06
93450 | 2025-06-02 |  | 2 | 160 | 160 | 0 | 0 |  | 0 |  | 0 | Y | M. Ebietsuwa | 2025-06-02
93452 | 2025-04-28 |  | 2 | 33 | 33 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-04-28
93454
93456
93458
93460 | 2025-04-30 |  | 2 | 30 | 30 | 0 | 0 |  | 0 |  |  | Y | E N Daniels | 2025-04-30
93462
93464
|  |  |  | 21353 | 21353

## Repeat Attacks 1
Unit No. | DATE | Status | Number of cars affected by graffiti/shadows on this unit | Total Number of Tags found | Total Tags Removed / Cleaned | Total Tags Not Cleaned on this Unit | Car Number (s) of Tags not cleaned (shadows) | Date of 2nd visit to clean remaining tags | Number of tags removed | Date of 3rd visit to clean remaining tags | Number of tags removed2 | Train Inspected and Fit for service (Y/N) | Inspected by Supervisor/Manager (Name) | Date of Completing all shadows (Tags) on this Unit excluding acid etched shadows | Car Number (s) of Tags not cleaned due to acid etched shadows
91001
91003 | [15 empty] | Total Trains | Total Units | Units Completed | % Completed
91005 | [15 empty] | 85 | =COUNTA(A:A)1 | =COUNTA(N:N)1 | #VALUE!
91007
91009
91011
91013
91015 | 01/06/2025 |  | 2 | 62 | 62 | 0 | 0 |  | 0 |  | 0 | Y | M. Ebietsuwa | 01/06/2025
91017
91019
91021
91023 | 07/05/2025 |  | 2 | 24 | 24 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 29/05/2025 | 91023/92023
91025
91027
91029
91031
91033
91035
91037 | 25/05/2025 |  | 2 | 220 | 220 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 25/05/2025
91039 | 06/05/2025 |  | 2 | 22 | 22 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 06/05/2025
91041
91043
91045
91047
91049
91051 | 28/05/2025 |  | 2 | 40 | 40 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 28/05/2025
91053
91055
91057
91059
91061
91063 | 24/06/2025 |  | 2 | 20 | 20 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 24/06/2025
91065 | 07/07/2025 |  | 2 | 104 | 104 | 0 | 0 |  | 0 |  | 0 | Y | M. Ebietsuwa | 07/07/2025
91067
91069
91071
91073
91075
91077
91079
91081
91083 | 08/07/2025 |  | 2 | 202 | 202 | 0 | 0 |  | 0 |  | 0 | Y | M. Ebietsuwa | 08/07/2025
91085
91087
91089
91091
91093
91095
91097 | 23/06/2025 |  | 2 | 50 | 50 | 0 | 0 |  | 0 |  | 0 | Y | E. Nyarko | 23/06/2025
91099
91101
91103
91105
91107
91109
91111
91113 | 03/06/2025 |  | 2 | 25 | 25 | 0 | 0 |  | 0 |  | 0 | Y | E. Nyarko | 03/06/2025
91115
91117
91119
91121
91123
91125 | 22/06/2025 |  | 2 | 130 | 130 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 22/06/2025
91127
91129 | 22/06/2025 |  | 2 | 130 | 130 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 22/06/2025
91131 | 03/06/2025 |  | 2 | 100 | 100 | 0 | 0 |  | 0 |  | 0 | Y | E. Nyarko | 03/06/2025
91133
91135
91137
91139 | 06/07/2025 |  | 2 | 180 | 180 | 0 | 0 |  | 0 |  | 0 | Y | M. Ebietsuwa | 06/07/2025
91141
91143
91145
91147
91149
91151
91153
91155
91157
91159
91161
91163
91165
91167
91169
91171
91173 | 2025-05-22 |  | 2 | 200 | 200 | 0 | 0 |  | 0 |  | 0 | Y | C. Ebietsuwa | 2025-05-22
91175 | 2025-05-15 |  | 2 | 120 | 120 | 0 | 0 |  | 0 |  | 0 | Y | Christopher | 2025-05-15
91177
91179 | 2025-06-11 |  | 2 | 206 | 206 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-06-11
91181
91183
91185 | 2025-07-04 |  | 2 | 168 | 168 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-07-04
91187
91189
91191
91193
91195
91197 | 2025-06-11 |  | 2 | 180 | 180 | 0 | 0 |  | 0 |  | 0 | Y | E. Nyarko | 2025-06-11
91199 | 2025-06-17 |  | 1 | 80 | 80 | 0 | 0 |  | 0 |  | 0 | Y | E. Nyarko | 2025-06-17
91201
91203
91205
91207
91209
91211 | 2025-05-26 |  | 2 | 60 | 60 | 0 | 0 |  | 0 |  | 0 | Y | M. Ebietsuwa | 2025-05-26
91213
91215
91217
91219
91221
91223
91225
91227
91229
91231
91233
91235
91237
91239
91241
91243
91245
91247
91249
91251
91253 | 2025-06-25 |  | 0 | 66 | 66 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-06-25
91255 | 2025-06-23 |  | 2 | 100 | 100 | 0 | 0 |  | 0 |  | 0 | Y | E. Nyarko | 2025-06-23
91257
91259 | 2025-06-10 |  | 2 | 360 | 360 | 0 | 0 |  | 0 |  | 0 | Y | M. Ebietsuwa | 2025-06-10
91261 | 2025-07-02 |  | 2 | 136 | 136 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-07-02
91263
91265
91267 | 2025-06-17 |  | 2 | 100 | 100 | 0 | 0 |  | 0 |  | 0 | Y | E. Nyarko | 2025-06-17
91269
91271 | 2025-06-24 |  | 1 | 80 | 80 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-06-24
91273
91275
91277 | 2025-05-20 |  | 2 | 245 | 245 | 0 | 0 |  | 0 |  | 0 | Y | C. Ebietsuwa | 2025-05-20
91279
91281
91283
91285
91287
91289
91291
91293
91295
91297
91299
91301
91303
91305
91307 | 2025-07-01 |  | 2 | 59 | 59 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-07-01
91309
91311
91313
91315 | 2025-06-23 |  | 2 | 50 | 50 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-06-23
91317 | 2025-06-04 |  | 2 | 180 | 180 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-06-04
91319
91321
91323
91325 | 2025-06-26 |  | 2 | 140 | 140 | 0 | 0 |  | 0 |  | 0 |  | M. Ebietsuwa | 2025-06-26
91327
91329
91331
91333 | 2025-06-24 |  | 2 | 20 | 20 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-06-24
91335
91337
91339
91341
91343
91345
91347
91349 | 2025-05-29 |  | 2 | 70 | 70 | 0 | 0 |  | 0 |  | 0 | Y | M. Ebietsuwa | 2025-05-29
93002
93004
93006 | 2025-05-29 |  | 2 | 180 | 180 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-05-29
93008
93010
93012
93014
93016 | 2025-07-01 |  | 2 | 14 | 14 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-07-01
93018
93020
93022
93024
93026
93028
93030
93032
93034
93036
93038
93040
93042
93044
93046
93048 | 2025-03-13 |  | 2 | 20 | 20 | 0 | 0 |  | 0 |  | 0 | Y | M. Ebietsuwa
93050
93052
93054
93056
93058 | 2025-06-22 |  | 2 | 120 | 120 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-06-22
93060
93062
93064
93066
93068
93070
93072
93074
93076 | 2025-05-06 |  | 2 | 22 | 22 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-05-06
93078
93080
93082
93084
93086
93088 | 2025-07-02 |  | 2 | 87 | 87 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-07-02
93090
93092
93094
93096
93098
93100
93102 | 2025-07-02 |  | 1 | 44 | 44 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-07-02
93104
93106
93108
93110
93112 | 2025-06-15 |  | 2 | 100 | 100 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-06-15
93114
93116 | 2025-05-25 |  | 2 | 80 | 80 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-05-25
93118
93120
93122
93124 | 2025-06-17 |  | 2 | 114 | 114 | 0 | 0 |  | 0 |  | 0 | Y | E. Nyarko | 2025-06-17
93126
93128 | 2025-05-11 |  | 2 | 24 | 24 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-05-11
93130
93132
93134
93136
93138
93140
93142
93144
93146
93148
93150
93152
93154
93156
93158
93160 | 2025-07-06 |  | 2 | 140 | 140 | 0 | 0 |  | 0 |  | 0 | Y | M. Ebietsuwa | 2025-07-06
93162
93164 | 2025-05-20 |  | 2 | 94 | 94 | 0 | 0 |  | 0 |  | 0 | Y | C. Ebietsuwa | 2025-05-20
93166
93168
93170
93172
93174 | 2025-06-11 |  | 2 | 214 | 214 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-06-11
93176
93178 | 2025-06-01 |  | 2 | 115 | 115 | 0 | 0 |  | 0 |  | 0 | Y | M. Ebietsuwa | 2025-06-01
93180
93182
93184
93186
93188
93190
93192
93194 | 2025-06-24 |  | 2 | 30 | 30 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-06-24
93196 | 2025-05-11 |  | 2 | 12 | 12 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-05-11
93198
93200
93202
93204
93206
93208
93210
93212
93214 | 2025-06-23 |  | 2 | 100 | 100 | 0 | 0 |  | 0 |  | 0 | Y | E. Nyarko | 2025-06-23
93216
93218
93220
93222
93224
93226
93228
93230
93232
93234
93236
93238
93240
93242
93244
93246
93248
93250
93252
93254
93256
93258
93260
93262
93264
93266
93402 | 2025-06-23 |  | 2 | 50 | 50 | 0 | 0 |  | 0 |  | 0 | Y | E. Nyarko | 2025-06-23
93404
93406 | 2025-07-02 |  | 2 | 77 | 77 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-07-02
93408
93410 | 2025-06-01 |  | 2 | 35 | 35 | 0 | 0 |  | 0 |  | 0 | Y | M. Ebietsuwa | 2025-06-01
93412
93414
93416
93418
93420
93422 | 2025-06-03 |  | 2 | 210 | 210 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-06-03
93424
93426
93428 | 2025-05-15 |  | 2 | 112 | 112 | 0 | 0 |  | 0 |  | 0 | Y | Christopher | 2025-05-15
93430 | 2025-06-15 |  | 2 | 140 | 140 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-06-15
93432
93434
93436 | 2025-06-03 |  | 2 | 160 | 160 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-06-03
93438
93440
93442
93444
93446
93448
93450
93452
93454
93456 | 2025-05-20 |  | 2 | 180 | 180 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-05-20
93458
93460
93462
93464

## Repeat Attacks 2
Unit No. | DATE | Status | Number of cars affected by graffiti/shadows on this unit | Total Number of Tags found | Total Tags Removed / Cleaned | Total Tags Not Cleaned on this Unit | Car Number (s) of Tags not cleaned (shadows) | Date of 2nd visit to clean remaining tags | Number of tags removed | Date of 3rd visit to clean remaining tags | Number of tags removed2 | Train Inspected and Fit for service (Y/N) | Inspected by Supervisor/Manager (Name) | Date of Completing all shadows (Tags) on this Unit excluding acid etched shadows | Car Number (s) of Tags not cleaned due to acid etched shadows
91001
91003 | [15 empty] | Total Trains | Total Units | Units Completed | % Completed
91005 | [15 empty] | 85 | =COUNTA(A:A)1 | =COUNTA(N:N)1 | #VALUE!
91007
91009
91011
91013
91015
91017
91019
91021
91023
91025
91027
91029
91031
91033
91035
91037
91039
91041
91043
91045
91047
91049
91051
91053
91055
91057
91059
91061
91063
91065
91067
91069
91071
91073
91075
91077
91079
91081
91083
91085
91087
91089
91091
91093
91095
91097
91099
91101
91103
91105
91107
91109
91111
91113 | 07/07/2025 |  | 2 | 60 | 60 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 07/07/2025
91115
91117
91119
91121
91123
91125 | 25/06/2025 |  | 2 | 88 | 88 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 25/06/2025
91127
91129
91131
91133
91135
91137
91139
91141
91143
91145
91147
91149
91151
91153
91155
91157
91159
91161
91163
91165
91167
91169
91171
91173
91175
91177
91179
91181
91183
91185
91187
91189
91191
91193
91195
91197
91199
91201
91203
91205
91207
91209
91211
91213
91215
91217
91219
91221
91223
91225
91227
91229
91231
91233
91235
91237
91239
91241
91243
91245
91247
91249
91251
91253
91255
91257
91259
91261
91263
91265
91267
91269
91271
91273
91275
91277
91279
91281
91283
91285
91287
91289
91291
91293
91295
91297
91299
91301
91303
91305
91307
91309
91311
91313
91315
91317 | 2025-06-09 |  | 2 | 222 | 222 | 0 | 0 |  | 0 |  | 0 | Y | M. Ebietsuwa | 2025-06-09
91319
91321
91323
91325
91327
91329
91331
91333
91335
91337
91339
91341
91343
91345
91347
91349
93002
93004
93006
93008
93010
93012
93014
93016
93018
93020
93022
93024
93026
93028
93030
93032
93034
93036
93038
93040
93042
93044
93046
93048
93050
93052
93054
93056
93058
93060
93062
93064
93066
93068
93070
93072
93074
93076
93078
93080
93082
93084
93086
93088
93090
93092
93094
93096
93098
93100
93102
93104
93106
93108
93110
93112
93114
93116
93118
93120
93122
93124
93126
93128
93130
93132
93134
93136
93138
93140
93142
93144
93146
93148
93150
93152
93154
93156
93158
93160
93162
93164
93166
93168
93170
93172
93174
93176
93178 | 2025-06-11 |  | 1 | 40 | 40 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-06-11
93180
93182
93184
93186
93188
93190
93192
93194
93196 | 2025-06-24 |  | 2 | 30 | 30 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-06-24
93198
93200
93202
93204
93206
93208
93210
93212
93214
93216
93218
93220
93222
93224
93226
93228
93230
93232
93234
93236
93238
93240
93242
93244
93246
93248
93250
93252
93254
93256
93258
93260
93262
93264
93266
93402
93404
93406
93408
93410
93412
93414
93416
93418
93420
93422
93424
93426
93428 | 2025-06-15 |  | 2 | 150 | 150 | 0 | 0 |  | 0 |  | 0 | Y | E N Daniels | 2025-06-15
93430
93432
93434
93436
93438
93440
93442
93444
93446
93448
93450
93452
93454
93456
93458
93460
93462
93464

## Repeat Attacks 3
Unit No. | DATE | Status | Number of cars affected by graffiti/shadows on this unit | Total Number of Tags found | Total Tags Removed / Cleaned | Total Tags Not Cleaned on this Unit | Car Number (s) of Tags not cleaned (shadows) | Date of 2nd visit to clean remaining tags | Number of tags removed | Date of 3rd visit to clean remaining tags | Number of tags removed2 | Train Inspected and Fit for service (Y/N) | Inspected by Supervisor/Manager (Name) | Date of Completing all shadows (Tags) on this Unit excluding acid etched shadows | Car Number (s) of Tags not cleaned due to acid etched shadows
91001
91003 | [15 empty] | Total Trains | Total Units | Units Completed | % Completed
91005 | [15 empty] | 85 | =COUNTA(A:A)1 | =COUNTA(N:N)1 | #VALUE!
91007
91009
91011
91013
91015
91017
91019
91021
91023
91025
91027
91029
91031
91033
91035
91037
91039
91041
91043
91045
91047
91049
91051
91053
91055
91057
91059
91061
91063
91065
91067
91069
91071
91073
91075
91077
91079
91081
91083
91085
91087
91089
91091
91093
91095
91097
91099
91101
91103
91105
91107
91109
91111
91113
91115
91117
91119
91121
91123
91125
91127
91129
91131
91133
91135
91137
91139
91141
91143
91145
91147
91149
91151
91153
91155
91157
91159
91161
91163
91165
91167
91169
91171
91173
91175
91177
91179
91181
91183
91185
91187
91189
91191
91193
91195
91197
91199
91201
91203
91205
91207
91209
91211
91213
91215
91217
91219
91221
91223
91225
91227
91229
91231
91233
91235
91237
91239
91241
91243
91245
91247
91249
91251
91253
91255
91257
91259
91261
91263
91265
91267
91269
91271
91273
91275
91277
91279
91281
91283
91285
91287
91289
91291
91293
91295
91297
91299
91301
91303
91305
91307
91309
91311
91313
91315
91317
91319
91321
91323
91325
91327
91329
91331
91333
91335
91337
91339
91341
91343
91345
91347
91349
93002
93004
93006
93008
93010
93012
93014
93016
93018
93020
93022
93024
93026
93028
93030
93032
93034
93036
93038
93040
93042
93044
93046
93048
93050
93052
93054
93056
93058
93060
93062
93064
93066
93068
93070
93072
93074
93076
93078
93080
93082
93084
93086
93088
93090
93092
93094
93096
93098
93100
93102
93104
93106
93108
93110
93112
93114
93116
93118
93120
93122
93124
93126
93128
93130
93132
93134
93136
93138
93140
93142
93144
93146
93148
93150
93152
93154
93156
93158
93160
93162
93164
93166
93168
93170
93172
93174
93176
93178 | 2025-06-25 |  | 2 | 66 | 66 | 0 | 0 |  | 0 |  | 0 | Y | M. Ebietsuwa | 2025-06-25
93180
93182
93184
93186
93188
93190
93192
93194
93196
93198
93200
93202
93204
93206
93208
93210
93212
93214
93216
93218
93220
93222
93224
93226
93228
93230
93232
93234
93236
93238
93240
93242
93244
93246
93248
93250
93252
93254
93256
93258
93260
93262
93264
93266
93402
93404
93406
93408
93410
93412
93414
93416
93418
93420
93422
93424
93426
93428
93430
93432
93434
93436
93438
93440
93442
93444
93446
93448
93450
93452
93454
93456
93458
93460
93462
93464

## Repeat Attacks 4
Unit No. | DATE | Status | Number of cars affected by graffiti/shadows on this unit | Total Number of Tags found | Total Tags Removed / Cleaned | Total Tags Not Cleaned on this Unit | Car Number (s) of Tags not cleaned (shadows) | Date of 2nd visit to clean remaining tags | Number of tags removed | Date of 3rd visit to clean remaining tags | Number of tags removed2 | Train Inspected and Fit for service (Y/N) | Inspected by Supervisor/Manager (Name) | Date of Completing all shadows (Tags) on this Unit excluding acid etched shadows | Car Number (s) of Tags not cleaned due to acid etched shadows
91001
91003 | [15 empty] | Total Trains | Total Units | Units Completed | % Completed
91005 | [15 empty] | 85 | 340 | 0 | 0
91007
91009
91011
91013
91015
91017
91019
91021
91023
91025
91027
91029
91031
91033
91035
91037
91039
91041
91043
91045
91047
91049
91051
91053
91055
91057
91059
91061
91063
91065
91067
91069
91071
91073
91075
91077
91079
91081
91083
91085
91087
91089
91091
91093
91095
91097
91099
91101
91103
91105
91107
91109
91111
91113
91115
91117
91119
91121
91123
91125
91127
91129
91131
91133
91135
91137
91139
91141
91143
91145
91147
91149
91151
91153
91155
91157
91159
91161
91163
91165
91167
91169
91171
91173
91175
91177
91179
91181
91183
91185
91187
91189
91191
91193
91195
91197
91199
91201
91203
91205
91207
91209
91211
91213
91215
91217
91219
91221
91223
91225
91227
91229
91231
91233
91235
91237
91239
91241
91243
91245
91247
91249
91251
91253
91255
91257
91259
91261
91263
91265
91267
91269
91271
91273
91275
91277
91279
91281
91283
91285
91287
91289
91291
91293
91295
91297
91299
91301
91303
91305
91307
91309
91311
91313
91315
91317
91319
91321
91323
91325
91327
91329
91331
91333
91335
91337
91339
91341
91343
91345
91347
91349
93002
93004
93006
93008
93010
93012
93014
93016
93018
93020
93022
93024
93026
93028
93030
93032
93034
93036
93038
93040
93042
93044
93046
93048
93050
93052
93054
93056
93058
93060
93062
93064
93066
93068
93070
93072
93074
93076
93078
93080
93082
93084
93086
93088
93090
93092
93094
93096
93098
93100
93102
93104
93106
93108
93110
93112
93114
93116
93118
93120
93122
93124
93126
93128
93130
93132
93134
93136
93138
93140
93142
93144
93146
93148
93150
93152
93154
93156
93158
93160
93162
93164
93166
93168
93170
93172
93174
93176
93178
93180
93182
93184
93186
93188
93190
93192
93194
93196
93198
93200
93202
93204
93206
93208
93210
93212
93214
93216
93218
93220
93222
93224
93226
93228
93230
93232
93234
93236
93238
93240
93242
93244
93246
93248
93250
93252
93254
93256
93258
93260
93262
93264
93266
93402
93404
93406
93408
93410
93412
93414
93416
93418
93420
93422
93424
93426
93428
93430
93432
93434
93436
93438
93440
93442
93444
93446
93448
93450
93452
93454
93456
93458
93460
93462
93464

## Repeat Attacks 5
Unit No. | DATE | Status | Number of cars affected by graffiti/shadows on this unit | Total Number of Tags found | Total Tags Removed / Cleaned | Total Tags Not Cleaned on this Unit | Car Number (s) of Tags not cleaned (shadows) | Date of 2nd visit to clean remaining tags | Number of tags removed | Date of 3rd visit to clean remaining tags | Number of tags removed2 | Train Inspected and Fit for service (Y/N) | Inspected by Supervisor/Manager (Name) | Date of Completing all shadows (Tags) on this Unit excluding acid etched shadows | Car Number (s) of Tags not cleaned due to acid etched shadows
91001
91003 | [15 empty] | Total Trains | Total Units | Units Completed | % Completed
91005 | [15 empty] | 85 | 340 | 0 | 0
91007
91009
91011
91013
91015
91017
91019
91021
91023
91025
91027
91029
91031
91033
91035
91037
91039
91041
91043
91045
91047
91049
91051
91053
91055
91057
91059
91061
91063
91065
91067
91069
91071
91073
91075
91077
91079
91081
91083
91085
91087
91089
91091
91093
91095
91097
91099
91101
91103
91105
91107
91109
91111
91113
91115
91117
91119
91121
91123
91125
91127
91129
91131
91133
91135
91137
91139
91141
91143
91145
91147
91149
91151
91153
91155
91157
91159
91161
91163
91165
91167
91169
91171
91173
91175
91177
91179
91181
91183
91185
91187
91189
91191
91193
91195
91197
91199
91201
91203
91205
91207
91209
91211
91213
91215
91217
91219
91221
91223
91225
91227
91229
91231
91233
91235
91237
91239
91241
91243
91245
91247
91249
91251
91253
91255
91257
91259
91261
91263
91265
91267
91269
91271
91273
91275
91277
91279
91281
91283
91285
91287
91289
91291
91293
91295
91297
91299
91301
91303
91305
91307
91309
91311
91313
91315
91317
91319
91321
91323
91325
91327
91329
91331
91333
91335
91337
91339
91341
91343
91345
91347
91349
93002
93004
93006
93008
93010
93012
93014
93016
93018
93020
93022
93024
93026
93028
93030
93032
93034
93036
93038
93040
93042
93044
93046
93048
93050
93052
93054
93056
93058
93060
93062
93064
93066
93068
93070
93072
93074
93076
93078
93080
93082
93084
93086
93088
93090
93092
93094
93096
93098
93100
93102
93104
93106
93108
93110
93112
93114
93116
93118
93120
93122
93124
93126
93128
93130
93132
93134
93136
93138
93140
93142
93144
93146
93148
93150
93152
93154
93156
93158
93160
93162
93164
93166
93168
93170
93172
93174
93176
93178
93180
93182
93184
93186
93188
93190
93192
93194
93196
93198
93200
93202
93204
93206
93208
93210
93212
93214
93216
93218
93220
93222
93224
93226
93228
93230
93232
93234
93236
93238
93240
93242
93244
93246
93248
93250
93252
93254
93256
93258
93260
93262
93264
93266
93402
93404
93406
93408
93410
93412
93414
93416
93418
93420
93422
93424
93426
93428
93430
93432
93434
93436
93438
93440
93442
93444
93446
93448
93450
93452
93454
93456
93458
93460
93462
93464

## Repeat Attack 6
Unit No. | DATE | Status | Number of cars affected by graffiti/shadows on this unit | Total Number of Tags found | Total Tags Removed / Cleaned | Total Tags Not Cleaned on this Unit | Car Number (s) of Tags not cleaned (shadows) | Date of 2nd visit to clean remaining tags | Number of tags removed | Date of 3rd visit to clean remaining tags | Number of tags removed2 | Train Inspected and Fit for service (Y/N) | Inspected by Supervisor/Manager (Name) | Date of Completing all shadows (Tags) on this Unit excluding acid etched shadows | Car Number (s) of Tags not cleaned due to acid etched shadows
91001
91003 | [15 empty] | Total Trains | Total Units | Units Completed | % Completed
91005 | [15 empty] | 85 | 340 | 0 | 0
91007
91009
91011
91013
91015
91017
91019
91021
91023
91025
91027
91029
91031
91033
91035
91037
91039
91041
91043
91045
91047
91049
91051
91053
91055
91057
91059
91061
91063
91065
91067
91069
91071
91073
91075
91077
91079
91081
91083
91085
91087
91089
91091
91093
91095
91097
91099
91101
91103
91105
91107
91109
91111
91113
91115
91117
91119
91121
91123
91125
91127
91129
91131
91133
91135
91137
91139
91141
91143
91145
91147
91149
91151
91153
91155
91157
91159
91161
91163
91165
91167
91169
91171
91173
91175
91177
91179
91181
91183
91185
91187
91189
91191
91193
91195
91197
91199
91201
91203
91205
91207
91209
91211
91213
91215
91217
91219
91221
91223
91225
91227
91229
91231
91233
91235
91237
91239
91241
91243
91245
91247
91249
91251
91253
91255
91257
91259
91261
91263
91265
91267
91269
91271
91273
91275
91277
91279
91281
91283
91285
91287
91289
91291
91293
91295
91297
91299
91301
91303
91305
91307
91309
91311
91313
91315
91317
91319
91321
91323
91325
91327
91329
91331
91333
91335
91337
91339
91341
91343
91345
91347
91349
93002
93004
93006
93008
93010
93012
93014
93016
93018
93020
93022
93024
93026
93028
93030
93032
93034
93036
93038
93040
93042
93044
93046
93048
93050
93052
93054
93056
93058
93060
93062
93064
93066
93068
93070
93072
93074
93076
93078
93080
93082
93084
93086
93088
93090
93092
93094
93096
93098
93100
93102
93104
93106
93108
93110
93112
93114
93116
93118
93120
93122
93124
93126
93128
93130
93132
93134
93136
93138
93140
93142
93144
93146
93148
93150
93152
93154
93156
93158
93160
93162
93164
93166
93168
93170
93172
93174
93176
93178
93180
93182
93184
93186
93188
93190
93192
93194
93196
93198
93200
93202
93204
93206
93208
93210
93212
93214
93216
93218
93220
93222
93224
93226
93228
93230
93232
93234
93236
93238
93240
93242
93244
93246
93248
93250
93252
93254
93256
93258
93260
93262
93264
93266
93402
93404
93406
93408
93410
93412
93414
93416
93418
93420
93422
93424
93426
93428
93430
93432
93434
93436
93438
93440
93442
93444
93446
93448
93450
93452
93454
93456
93458
93460
93462
93464