## District Line
Unit No. | DATE | Status | Number of cars affected by graffiti/shadows on this unit | Total Number of Tags found | Total Tags Removed / Cleaned | Total Tags Not Cleaned on this Unit | Car Number (s) of Tags not cleaned (shadows) | Date of 2nd visit to clean remaining tags | Number of tags removed | Date of 3rd visit to clean remaining tags | Number of tags removed2 | Train Inspected and Fit for service (Y/N) | Inspected by Supervisor/Manager (Name) | Date of Completing all shadows (Tags) on this Unit excluding acid etched shadows | Car Number (s) of Tags not cleaned due to acid etched shadows
21302 | 2025-10-20 | Service Train | 2 | 34 | 34 | 0 | 0 |  |  |  |  | Y | M Fernandes |  |  | Total Units Completed
21304 | 2025-10-28 | Service Train | 5 | 49 | 49 | 0 | 0 |  |  |  |  | Y | M KAZI |  |  | Total Trains | Total Units | Units Compled | % Completed
21306 | 2025-10-30 | SErvice Train | 5 | 13 | 13 | 0 | 0 |  |  |  |  | Y | M.Fernandes |  |  | 133 | 266 | 0 | 0
21308 | 2025-10-31 | Service Train | 7 | 55 | 55 | 0 | 0 |  |  |  |  | Y | M Fernandes
21310 | 2025-10-22 | Service Train | 6 | 35 | 35 | 0 | 0 |  |  |  |  | Y | M KAZI
21312 | 2025-11-01 | Service Train | 5 | 40 | 40 | 0 | 0 |  |  |  |  | Y | V Vasileva
21314 | 2025-10-27 | Service Train | 4 | 14 | 14 | 0 | 0 |  |  |  |  | Y | M Fernandes
21316
21318
21320 | 2025-10-30 | Service Train | 7 | 75 | 75 | 0 | 0 |  |  |  |  | Y | Thomas Lomax
21322 | 2025-10-21 | Service Train | 6 | 77 | 77 | 0 | 0 |  |  |  |  | Y | M KAZI
21326
21328 | 2025-10-28 | Stopped Train | 6 | 71 | 71 | 0 | 0 |  |  |  |  | y | M KAZI
21330 | 2025-10-26 | Service Train | 1 | 24 | 24 | 0 | 0 |  |  |  |  | Y | Thomas Lomax
21332 | 2025-10-25 | Service Train | 5 | 81 | 81 | 0 | 0 |  |  |  |  | Y | M KAZI
21334 | 2025-10-16 | Service Train | 2 | 12 | 12 | 0 | 0 |  |  |  |  | Y | V Vasileva
21336 | 2025-10-26 | Service Train | 1 | 1 | 1 | 0 | 0 |  |  |  |  | Y | Thomas Lomax
21338 | 2025-10-19 | Service Train | 4 | 13 | 13 | [6 empty] | Y | Thomas Lomax
21340 | 2025-10-24 | Service Train | 6 | 34 | 34 | 0 | 0 |  |  |  |  | Y | M KAZI
21342 | 2025-10-18 | Service Train | 2 | 7 | 7 | 0 | 0 |  |  |  |  | Y | V Vasileva
21344 | 2025-10-29 | Service Train | 7 | 52 | 52 | 0 | 0 |  |  |  |  | Y | M KAZI
21346 | 2025-10-26 | Service Train | 2 | 24 | 24 | 0 | 0 |  |  |  |  | Y | Thomas Lomax
21348 | 2025-10-15 | Service Train | 5 | 51 | 51 | 0 | 0 |  |  |  |  | Y | M KAZI
21350 | 2025-10-20 | Service Train | 6 | 45 | 45 | 0 | 0 |  |  |  |  | Y | M KAZI
21352 | 2025-10-15 | Service Train | 1 | 4 | 4 | 0 | 0 |  |  |  |  | Y | M Fernandes
21354 | 2025-10-27 | Service Train | 7 | 85 | 73 | 12 | 12
21356 | 2025-10-22 | Service Train | 5 | 21 | 21 | 0 | 0 |  |  |  |  | Y | M Fernandes
21358
21360 | 2025-10-18 | Service Train | 1 | 6 | 6 | 0 | 0 |  |  |  |  | Y | V Vasileva
21362 | 2025-10-20 | Service Train | 2 | 4 | 4 | 0 | 0 |  |  |  |  | Y | M Fernandes
21364 | 2025-10-20 | Service Train | 5 | 30 | 30 | 0 | 0 |  |  |  |  | Y | M KAZI
21366 | 2025-10-28 | Service Train | 4 | 13 | 13 | 0 | 0 |  |  |  |  | Y | V Vasileva
21368
21370 | 2025-10-23 | Service Train | 4 | 6 | 6 | 0 | 0 |  |  |  |  | Y | V Vasileva
21372 | 2025-10-26 | Stopped Train | 3 | 22 | 22 | 0 | 0 |  |  |  |  | Y | M Fernandes
21374
21376 | 2025-10-28 | Service Train | 3 | 16 | 16 | 0 | 0 |  |  |  |  | Y | V Vasileva
21378 | 2025-10-16 | Service Train | 2 | 25 | 25 | 0 | 0 |  |  |  |  | Y | V Vasileva
21380
21382
21383 | 2025-10-20 | Service Train | 1 | 4 | 4 | 0 | 0 |  |  |  |  | Y | M Fernandes
21386 | 2025-10-15 | Service Train | 1 | 1 | 1 | 0 | 0 |  |  |  |  | Y | M Fernandes
21388 | 2025-10-29 | Service Train | 7 | 21 | 21 | 0 | 0 |  |  |  |  | Y | M Fernandes
21390 | 2025-10-25 | Service Train | 5 | 67 | 67 | 0 | 0 |  |  |  |  | Y | M KAZI
21392 | 2025-10-20 | Service Train | 3 | 97 | 97 | 0 | 0 |  |  |  |  | Y | M KAZI
21394 | 2025-10-16 | Service Train | 1 | 4 | 4 | 0 | 0 |  |  |  |  | Y | V Vasileva
21396 | 2025-10-20 | Service Train | 2 | 7 | 7 | 0 | 0 |  |  |  |  | Y | M Fernandes
21398
21400
21402 | 2025-10-23 | Service Train | 6 | 195 | 195 | 0 | 0 |  |  |  |  | Y | M KAZI
21404
21406 | 2025-10-24 | Service Train | 5 | 25 | 25 | 0 | 0 |  |  |  |  | Y | M Fernandes
21408
21410 | 2025-10-21 | Service Train | 2 | 6 | 6 | 0 | 0 |  |  |  |  | Y | V Vasileva
21412 | 2025-10-30 | Service Train | 4 | 24 | 24 | 0 | 0 |  |  |  |  | Y | M.Fernandes
21414 | 2025-10-20 | Service Train | 3 | 8 | 8 | 0 | 0 |  |  |  |  | Y | M KAZI
21416
21418 | 2025-10-30 | Service Train | 3 | 21 | 21 | 0 | 0 |  |  |  |  | Y | V Vasileva
21420 | 2025-10-24 | Service Train | 1 | 55 | 55 | 0 | 0 |  |  |  |  | Y | M Fernandes
21422 | 2025-10-30 | Service Train | 7 | 155 | 155 | 0 | 0 |  |  |  |  | Y | Thomas Lomax
21424 | 2025-10-29 | Service Train | 6 | 118 | 118 | 0 | 0 |  |  |  |  | Y | M KAZI
21426 | 2025-10-23 | Service Train | 3 | 7 | 7 | 0 | 0 |  |  |  |  | Y | V Vasileva
21428 | 2025-10-19 | Service Train | 1 | 10 | 10 | [6 empty] | Y | Thomas Lomax
21430 | 2025-10-17 |  | 4 | 120 | 120 | [6 empty] | Y | M KAZI
21432 | 2025-10-21 | Service Train | 5 | 33 | 33 | 0 | 0 |  |  |  |  | Y | V Vasileva
21434 | 2025-10-17 |  | 3 | 60 | 60 | [6 empty] | Y | M KAZI
21436 | 2025-10-29 | Service Train | 6 | 29 | 29 | 0 | 0 |  |  |  |  | Y | M Fernandes
21438 | 2025-10-22 | Service Train | 5 | 85 | 85 | 0 | 0 |  |  |  |  | Y | M KAZI
21440 | 2025-11-02 | Service Train | 2 | 31 | 31 | 0 | 0 |  |  |  |  | y | M Fernandes
21442
21444 | 2025-10-31 | S | 5 | 108 | 108 | 0 | 0 |  |  |  |  | Y | M KAZI
21446
21448 | 2025-10-17 |  | 2 | 50 | 50 | [6 empty] | Y | M KAZI
21450 | 2025-10-26 | Stopped Train | 4 | 19 | 19 | 0 | 0 |  |  |  |  | Y | M Fernandes
21452 | 2025-10-27 | Service Train | 6 | 134 | 134 | 0 | 0 |  |  |  |  | Y | M KAZI
21454 | 2025-10-30 | Service Train | 4 | 153 | 153 | 0 | 0 |  |  |  |  | Y | Thomas Lomax
21456 | 2025-10-26 | Service Train | 2 | 9 | 9 | 0 | 0 |  |  |  |  | Y | Thomas Lomax
21458 | 2025-10-16 | Service Train | 1 | 8 | 8 | 0 | 0 |  |  |  |  | Y | V Vasileva
21460
21462 | 2025-10-24 | Service Train | 6 | 117 | 117 | 0 | 0 |  |  |  |  | Y | M KAZI
21464
21466 | 2025-10-16 | Service Train | 5 | 42 | 42 | 0 | 0 |  |  |  |  | Y | M KAZI
21468 | 2025-10-24 | Service Train | 5 | 126 | 126 | 0 | 0 |  |  |  |  | Y | M KAZI
21470
21472 | 2025-10-26 | Service Train | 2 | 4 | 4 | 0 | 0 |  |  |  |  | Y | Thomas Lomax
21474 | 2025-10-23 | Service Train | 1 | 3 | 3 | 0 | 0 |  |  |  |  | Y | V Vasileva
21476 | 2025-10-27 | Service Train | 7 | 123 | 123 | 0 | 0 |  |  |  |  | Y | M KAZI
21478 | 2025-10-28 | Service Train | 7 | 48 | 48 | 0 | 0 |  |  |  |  | Y | V Vasileva
21480 | 2025-10-25 |  | 2 | 18 | 18 | 0 | 0 |  |  |  |  | Y | V Vasileva
21482 | 2025-10-18 | Service Train | 1 | 2 | 2 | 0 | 0 |  |  |  |  | Y | V Vasileva
21484 | 2025-10-19 | Service Train | 1 | 2 | 2 | [6 empty] | Y | Thomas Lomax
21486 | 2025-10-17 |  | 4 | 50 | 50 | 0 | 0 |  |  |  |  | Y | M Kazi
21488 | 2025-10-31 | Service Train | 2 | 7 | 7 | 0 | 0 |  |  |  |  | Y | M Fernandes
21490 | 2025-10-29 | Service Train | 7 | 160 | 160 | 0 | 0 |  |  |  |  | Y | M KAZI
21492 | 2025-10-20 | Service Train | 1 | 18 | 18 | 0 | 0 |  |  |  |  | Y | M Fernandes
21494 | 2025-10-22 | Service Train | 6 | 24 | 24 | 0 | 0 |  |  |  |  | Y | M KAZI
21496 | 2025-10-15 | Service Train | 1 | 2 | 2 | 0 | 0 |  |  |  |  | Y | M Fernandes
21498
21500 | 2025-10-22 | Service Train | 5 | 15 | 15 | 0 | 0 |  |  |  |  | Y | M Fernandes
21502 | 2025-10-20 | Service Train | 2 | 13 | 13 | 0 | 0 |  |  |  |  | Y | M Fernandes
21504 | 2025-10-20 | Service Train | 2 | 4 | 4 | 0 | 0 |  |  |  |  | Y | M Fernandes
21506
21508 | 2025-10-16 | Service Train | 5 | 11 | 11 | 0 | 0 |  |  |  |  | Y | M KAZI
21510 | 2025-10-27 | Service Train | 1 | 2 | 2 | 0 | 0 |  |  |  |  | Y | M Fernandes
21512 | 2025-10-31 | Service Train | 1 | 2 | 2 | 0 | 0 |  |  |  |  | Y | M Fernandes
21514 | 2025-10-22 | Service Train | 6 | 18 | 18 | 0 | 0 |  |  |  |  | Y | M KAZI
21516
21518 | 2025-10-20 | Service Train | 1 | 1 | 1 | 0 | 0 |  |  |  |  | Y | M Fernandes
21520 | 2025-10-21 | Service Train | 4 | 116 | 116 | 0 | 0 |  |  |  |  | Y | M KAZI
21522 | 2025-10-18 | Service Train | 7 | 279 | 279 | 0 | 0 |  |  |  |  | Y | M KAZI
21524 | 2025-10-17 | Service Train | 4 | 40 | 40 | [6 empty] | Y | M KAZI
21526 | 2025-10-17 | Service Train | 2 | 14 | 14 | [6 empty] | Y | M KAZI
21528
21530 | 2025-10-19 | Service Train | 1 | 230 | 230 | 0 | 0 |  |  |  |  | Y | M Fernandes
21532 | 2025-10-31 | Service Train | 2 | 3 | 3 | 0 | 0 |  |  |  |  | Y | M Fernandes
21534 | 2025-10-28 | Service Train | 6 | 61 | 61 | 0 | 0 |  |  |  |  | Y | M KAZI
21536
21538 | 2025-10-15 | Service Train | 5 | 181 | 181 | 0 | 0 |  |  |  |  | Y | M KAZI
21540 | 2025-10-21 | Service Train | 2 | 14 | 14 | 0 | 0 |  |  |  |  | Y | V Vasileva
21542 | 2025-10-16 | Service Train | 7 | 110 | 110 | 0 | 0 |  |  |  |  | Y | M KAZI
21544 | 2025-10-19 | Service Train | 2 | 20 | 20 | [6 empty] | Y | Thomas Lomax
21546
21548
21550 | 2025-10-21 | Service Train | 5 | 76 | 76 | 0 | 0 |  |  |  |  | Y | M KAZI
21552 | 2025-10-31 | Service Train | 4 | 123 | 123 | 0 | 0 |  |  |  |  | Y | M KAZI
21554 | 2025-10-30 | Service Train | 2 | 12 | 12 | 0 | 0 |  |  |  |  | Y | V Vasileva
21556 | 2025-10-25 |  | 5 | 41 | 41 | 0 | 0 |  |  |  |  | Y | V Vasileva
21558 | 2025-10-29 | Service Train | 4 | 30 | 30 | 0 | 0 |  |  |  |  | Y | M KAZI
21560
21562
21564 | 2025-10-24 | Service Train | 4 | 162 | 162 | 0 | 0 |  |  |  |  | Y | M KAZI
21566 | 2025-11-01 |  | 3 | 39 | 39 | 0 | 0 |  |  |  |  | Y | V Vasileva
21568
21301
21303
21305
21307
21309
21311
21313
21315
21317
21319
21321
21325
21327
21329
21331
21333
21335
21337
21339
21341
21343
21345
21347
21349
21351
21353
21355
21357
21359
21361
21363
21365
21367
21369
21371
21373
21375
21377
21379
21381
21384
21385
21387
21389
21391
21393
21395
21397
21399
21401
21403
21405
21407
21409
21411
21413
21415
21417
21419
21421
21423
21425
21427
21429 | 2025-10-17 |  | 3 | 107 | 107 | [6 empty] | Y | M kazi
21431
21433 | 2025-10-17 |  | 2 | 28 | 28 | [6 empty] | Y | M Kazi
21435
21437
21439
21441
21443
21445
21447 | 2025-10-17 |  | 2 | 32 | 32 | [6 empty] | Y | M Kazi
21449
21451
21453 | 2025-10-17 |  | 1 | 2 | 2 | [6 empty] | Y | M Fernandes
21455
21457
21459
21461
21463
21465
21467
21469
21471
21473
21475
21477
21479
21481
21483
21485 | 2025-10-17 |  | 3 | 45 | 45 | 0 | 0 |  |  |  |  | Y | M Kazi
21487
21489
21491
21493
21495
21497
21499
21501
21503
21505
21507
21509
21511
21513
21515
21517
21519
21521
21523 | 2025-10-17 |  | 3 | 32 | 32 | [6 empty] | Y | M Kazi
21525
21527
21529
21531
21533
21535
21537
21539
21541
21543
21545
21547
21549
21551
21553
21555
21557
21559
21561
21563
21565
21567

## Repeat Attacks 1
Unit No. | DATE | Status | Number of cars affected by graffiti/shadows on this unit | Total Number of Tags found | Total Tags Removed / Cleaned | Total Tags Not Cleaned on this Unit | Car Number (s) of Tags not cleaned (shadows) | Date of 2nd visit to clean remaining tags | Number of tags removed | Date of 3rd visit to clean remaining tags | Number of tags removed2 | Train Inspected and Fit for service (Y/N) | Inspected by Supervisor/Manager (Name) | Date of Completing all shadows (Tags) on this Unit excluding acid etched shadows | Car Number (s) of Tags not cleaned due to acid etched shadows
21302 | [15 empty] | Total Units Completed
21304 | [15 empty] | Total Trains | Total Units | Units Compled | % Completed
21306 | 2025-10-30 | Service Train | 6 | 13 | 13 | 0 | 0 |  |  |  |  | Y | V Vasileva |  |  | 133 | 266 | 0 | 0
21308
21310
21312
21314
21316
21318
21320 | 2025-10-30 | Service Train | 7 | 75 | 75 | 0 | 0
21322
21326
21328
21330
21332
21334 | 2025-10-22 | Service Train | 2 | 30 | 30 | 0 | 0 |  |  |  |  | Y | M Fernandes
21336
21338 | 2025-10-31 | Service Train | 3 | 8 | 8 | 0 | 0 |  |  |  |  | Y | M Fernandes
21340 | 2025-10-17 |  | 2 | 17 | 17 | 0 | 0 |  |  |  |  | Y | M Fernandes
21342 | 2025-11-02 | Service Train | 6 | 59 | 59 | 0 | 0 |  |  |  |  | y | T.Lomax
21344
21346 | 2025-10-30 | Service Train | 4 | 21 | 21 | 0 | 0 |  |  |  |  | Y | V Vasileva
21348 | 2025-10-24 | Service Train | 2 | 4 | 4 | 0 | 0 |  |  |  |  | Y | M Fernandes
21350
21352 | 2025-10-23 | Service Train | 3 | 8 | 8 | 0 | 0 |  |  |  |  | Y | V Vasileva
21354
21356 | 2025-11-02 | Service Train | 7 | 40 | 40 | 0 | 0 |  |  |  |  | Y | T.Lomax
21358
21360 | 2025-10-24 | Service Train | 3 | 16 | 16 | 0 | 0 |  |  |  |  | Y | M Fernandes
21362
21364
21366 | 2025-10-30 | Service Train | 1 | 3 | 3 | 0 | 0 |  |  |  |  | Y | M. Fernandes
21368
21370
21372
21374
21376
21378
21380
21382
21383
21386 | 2025-10-17 |  | 3 | 30 | 30 | [6 empty] | Y | M Fernandes
21388
21390
21392
21394 | 2025-11-01 | Service Train | 1 | 2 | 2 | 0 | 0 |  |  |  |  | Y | M KAZI
21396 | 2025-10-22 | Service Train | 4 | 96 | 96 | 0 | 0 |  |  |  |  | Y | M KAZI
21398
21400
21402 | 2025-10-31 | Service Train | 2 | 15 | 15 | 0 | 0 |  |  |  |  | Y | M KAZI
21404
21406
21408
21410 | 2025-10-24 | Service Train | 1 | 5 | 5 | 0 | 0 |  |  |  |  | Y | M Fernandes
21412 | 2025-10-30 | Service Train | 4 | 24 | 24 | 0 | 0 |  |  |  |  | Y | V Vasileva
21414
21416
21418 | 2025-10-30 | service Train | 3 | 21 | 21 | 0 | 0 |  |  |  |  | Y | M. Fernandes
21420
21422 | 2025-10-30 | Service Train | 7 | 155 | 155 | 0 | 0 |  |  |  |  | Y | T Lomax
21424
21426
21428
21430
21432
21434
21436
21438
21440
21442
21444
21446
21448
21450
21452
21454 | 2025-10-30 | Service Train | 4 | 153 | 153 | 0 | 0 |  |  |  |  | Y | T. Lomax
21456 | 2025-11-02 | Service Train | 1 | 1 | 1 | 0 | 0 |  |  |  |  | Y | T.Lomax
21458 | 2025-10-17 | Service Train | 1 | 4 | 4 | 0 | 0 |  |  |  |  | Y | M Fernandes
21460
21462
21464
21466
21468
21470
21472 | 2025-10-27 | Service Train | 2 | 7 | 7 | 0 | 0 |  |  |  |  | Y | M Fernandes
21474 | 2025-10-30 | Service Train | 2 | 8 | 8 | 0 | 0 |  |  |  |  | Y | V Vasileva
21476
21478 | 2025-11-01 | Service Train | 5 | 58 | 58 | 0 | 0 | 2025-11-02 | 2 |  |  | Y | M KAZI
21480 | 2025-11-02 | Service Train | 4 | 18 | 18 | 0 | 0 |  |  |  |  | Y | T. Lomax
21482 | 2025-10-27 | Service Train | 2 | 5 | 5 | 0 | 0 |  |  |  |  | Y | M Fernandes
21484 | 2025-10-28 | Service Train | 6 | 90 | 90 | 0 | 0 |  |  |  |  | Y | M KAZI
21486 | 2025-10-23 | Service Train | 4 | 6 | 6 | 0 | 0 |  |  |  |  | Y | V Vasileva
21488
21490
21492
21494
21496
21498
21500
21502
21504 | 2025-10-27 | Service Train | 2 | 9 | 9 | 0 | 0 |  |  |  |  | Y | M Fernandes
21506
21508
21510
21512
21514
21516
21518
21520
21522
21524
21526 | 2025-10-22 | Service Train | 3 | 8 | 8 | 0 | 0 |  |  |  |  | Y | M Fernandes
21528
21530
21532
21534
21536
21538 | 2025-10-29 | Service Train | 3 | 13 | 13 | 0 | 0 |  |  |  |  | Y | M Fernandes
21540
21542
21544
21546
21548
21550
21552
21554 | 2025-10-30 | Service Train | 2 | 12 | 12 | 0 | 0 |  |  |  |  | Y | M Fernandes
21556
21558
21560
21562
21564
21566
21568 | 2025-11-01 | Service Train | 6 | 80 | 80 | 0 | 0 |  |  |  |  | Y | M KAZI
21301
21303
21305
21307
21309
21311
21313
21315
21317
21319
21321
21325
21327
21329
21331
21333
21335
21337
21339
21341
21343
21345
21347
21349
21351
21353
21355
21357
21359
21361
21363
21365
21367
21369
21371
21373
21375
21377
21379
21381
21384
21385 | 2025-10-17 |  | 2 | 13 | 13 | [6 empty] | Y | M Fernandes
21387
21389
21391
21393
21395
21397
21399
21401
21403
21405
21407
21409
21411
21413
21415
21417
21419
21421
21423
21425
21427
21429
21431
21433
21435
21437
21439
21441
21443
21445
21447
21449
21451
21453
21455
21457
21459
21461
21463
21465
21467
21469
21471
21473
21475
21477
21479
21481
21483
21485
21487
21489
21491
21493
21495
21497
21499
21501
21503
21505
21507
21509
21511
21513
21515
21517
21519
21521
21523
21525
21527
21529
21531
21533
21535
21537
21539
21541
21543
21545
21547
21549
21551
21553
21555
21557
21559
21561
21563
21565
21567

## Repeat Attacks 2
Unit No. | DATE | Status | Number of cars affected by graffiti/shadows on this unit | Total Number of Tags found | Total Tags Removed / Cleaned | Total Tags Not Cleaned on this Unit | Car Number (s) of Tags not cleaned (shadows) | Date of 2nd visit to clean remaining tags | Number of tags removed | Date of 3rd visit to clean remaining tags | Number of tags removed2 | Train Inspected and Fit for service (Y/N) | Inspected by Supervisor/Manager (Name) | Date of Completing all shadows (Tags) on this Unit excluding acid etched shadows | Car Number (s) of Tags not cleaned due to acid etched shadows
21302 | [15 empty] | Total Units Completed
21304 | [15 empty] | Total Trains | Total Units | Units Compled | % Completed
21306 | 2025-10-30 | Service Train | 5 | 13 | 13 | 0 | 0 |  |  |  |  | Y | M Fernandes |  |  | 133 | 266 | 0 | 0
21308
21310
21312
21314
21316
21318
21320
21322
21326
21328
21330
21332
21334
21336
21338
21340
21342
21344
21346 | 2025-10-31 | Service Train | 4 | 21 | 21 | 0 | 0 |  |  |  |  | y | M Fernandes
21348
21350
21352 | 2025-10-27 | Service Train | 1 | 10 | 10 | 0 | 0 |  |  |  |  | Y | M Fernandes
21354
21356
21358
21360 | 2025-10-30 | Service Train | 2 | 6 | 6 | 0 | 0 |  |  |  |  | Y | V Vasileva
21362
21364
21366
21368
21370
21372
21374
21376
21378
21380
21382
21383
21386
21388
21390
21392
21394
21396
21398
21400
21402
21404
21406
21408
21410 | 2025-10-25 |  | 3 | 7 | 7 | 0 | 0 |  |  |  |  | Y | V Vasileva
21412
21414
21416
21418
21420
21422
21424
21426
21428
21430
21432
21434
21436
21438
21440
21442
21444
21446
21448
21450
21452
21454
21456
21458
21460
21462
21464
21466
21468 | 2025-10-31 | Service Train | 3 | 11 | 11 | 0 | 0 |  |  |  |  | Y | M KAZI
21470
21472
21474
21476
21478
21480
21482
21484
21486
21488
21490
21492
21494
21496
21498
21500
21502
21504
21506
21508
21510
21512
21514
21516
21518
21520
21522
21524
21526
21528
21530
21532
21534
21536
21538
21540
21542
21544
21546
21548
21550
21552
21554
21556
21558
21560
21562
21564
21566
21568
21301
21303
21305
21307
21309
21311
21313
21315
21317
21319
21321
21325
21327
21329
21331
21333
21335
21337
21339
21341
21343
21345
21347
21349
21351
21353
21355
21357
21359
21361
21363
21365
21367
21369
21371
21373
21375
21377
21379
21381
21384
21385
21387
21389
21391
21393
21395
21397
21399
21401
21403
21405
21407
21409
21411
21413
21415
21417
21419
21421
21423
21425
21427
21429
21431
21433
21435
21437
21439
21441
21443
21445
21447
21449
21451
21453
21455
21457
21459
21461
21463
21465
21467
21469
21471
21473
21475
21477
21479
21481
21483
21485
21487
21489
21491
21493
21495
21497
21499
21501
21503
21505
21507
21509
21511
21513
21515
21517
21519
21521
21523
21525
21527
21529
21531
21533
21535
21537
21539
21541
21543
21545
21547
21549
21551
21553
21555
21557
21559
21561
21563
21565
21567

## Repeat Attacks 3
Unit No. | DATE | Status | Number of cars affected by graffiti/shadows on this unit | Total Number of Tags found | Total Tags Removed / Cleaned | Total Tags Not Cleaned on this Unit | Car Number (s) of Tags not cleaned (shadows) | Date of 2nd visit to clean remaining tags | Number of tags removed | Date of 3rd visit to clean remaining tags | Number of tags removed2 | Train Inspected and Fit for service (Y/N) | Inspected by Supervisor/Manager (Name) | Date of Completing all shadows (Tags) on this Unit excluding acid etched shadows | Car Number (s) of Tags not cleaned due to acid etched shadows
21302 | [15 empty] | Total Units Completed
21304 | [15 empty] | Total Trains | Total Units | Units Compled | % Completed
21306 | [15 empty] | 133 | 266 | 0 | 0
21308
21310
21312
21314
21316
21318
21320
21322
21326
21328
21330
21332
21334
21336
21338
21340
21342
21344
21346
21348
21350
21352 | 2025-10-28 | Service Train | 6 | 46 | 46 | 0 | 0 |  |  |  |  | Y | M KAZI
21354
21356
21358
21360 | 2025-10-31 | Service Train | 3 | 6 | 6 | 0 | 0 |  |  |  |  | Y | M. Fernandes
21362
21364
21366
21368
21370
21372
21374
21376
21378
21380
21382
21383
21386
21388
21390
21392
21394
21396
21398
21400
21402
21404
21406
21408
21410
21412
21414
21416
21418
21420
21422
21424
21426
21428
21430
21432
21434
21436
21438
21440
21442
21444
21446
21448
21450
21452
21454
21456
21458
21460
21462
21464
21466
21468
21470
21472
21474
21476
21478
21480
21482
21484
21486
21488
21490
21492
21494
21496
21498
21500
21502
21504
21506
21508
21510
21512
21514
21516
21518
21520
21522
21524
21526
21528
21530
21532
21534
21536
21538
21540
21542
21544
21546
21548
21550
21552
21554
21556
21558
21560
21562
21564
21566
21568
21301
21303
21305
21307
21309
21311
21313
21315
21317
21319
21321
21325
21327
21329
21331
21333
21335
21337
21339
21341
21343
21345
21347
21349
21351
21353
21355
21357
21359
21361
21363
21365
21367
21369
21371
21373
21375
21377
21379
21381
21384
21385
21387
21389
21391
21393
21395
21397
21399
21401
21403
21405
21407
21409
21411
21413
21415
21417
21419
21421
21423
21425
21427
21429
21431
21433
21435
21437
21439
21441
21443
21445
21447
21449
21451
21453
21455
21457
21459
21461
21463
21465
21467
21469
21471
21473
21475
21477
21479
21481
21483
21485
21487
21489
21491
21493
21495
21497
21499
21501
21503
21505
21507
21509
21511
21513
21515
21517
21519
21521
21523
21525
21527
21529
21531
21533
21535
21537
21539
21541
21543
21545
21547
21549
21551
21553
21555
21557
21559
21561
21563
21565
21567

## Repeat Attacks 4
Unit No. | DATE | Status | Number of cars affected by graffiti/shadows on this unit | Total Number of Tags found | Total Tags Removed / Cleaned | Total Tags Not Cleaned on this Unit | Car Number (s) of Tags not cleaned (shadows) | Date of 2nd visit to clean remaining tags | Number of tags removed | Date of 3rd visit to clean remaining tags | Number of tags removed2 | Train Inspected and Fit for service (Y/N) | Inspected by Supervisor/Manager (Name) | Date of Completing all shadows (Tags) on this Unit excluding acid etched shadows | Car Number (s) of Tags not cleaned due to acid etched shadows
21302 | [15 empty] | Total Units Completed
21304 | [15 empty] | Total Trains | Total Units | Units Compled | % Completed
21306 | [15 empty] | 133 | 266 | 0 | 0
21308
21310
21312
21314
21316
21318
21320
21322
21326
21328
21330
21332
21334
21336
21338
21340
21342
21344
21346
21348
21350
21352
21354
21356
21358
21360
21362
21364
21366
21368
21370
21372
21374
21376
21378
21380
21382
21383
21386
21388
21390
21392
21394
21396
21398
21400
21402
21404
21406
21408
21410
21412
21414
21416
21418
21420
21422
21424
21426
21428
21430
21432
21434
21436
21438
21440
21442
21444
21446
21448
21450
21452
21454
21456
21458
21460
21462
21464
21466
21468
21470
21472
21474
21476
21478
21480
21482
21484
21486
21488
21490
21492
21494
21496
21498
21500
21502
21504
21506
21508
21510
21512
21514
21516
21518
21520
21522
21524
21526
21528
21530
21532
21534
21536
21538
21540
21542
21544
21546
21548
21550
21552
21554
21556
21558
21560
21562
21564
21566
21568
21301
21303
21305
21307
21309
21311
21313
21315
21317
21319
21321
21325
21327
21329
21331
21333
21335
21337
21339
21341
21343
21345
21347
21349
21351
21353
21355
21357
21359
21361
21363
21365
21367
21369
21371
21373
21375
21377
21379
21381
21384
21385
21387
21389
21391
21393
21395
21397
21399
21401
21403
21405
21407
21409
21411
21413
21415
21417
21419
21421
21423
21425
21427
21429
21431
21433
21435
21437
21439
21441
21443
21445
21447
21449
21451
21453
21455
21457
21459
21461
21463
21465
21467
21469
21471
21473
21475
21477
21479
21481
21483
21485
21487
21489
21491
21493
21495
21497
21499
21501
21503
21505
21507
21509
21511
21513
21515
21517
21519
21521
21523
21525
21527
21529
21531
21533
21535
21537
21539
21541
21543
21545
21547
21549
21551
21553
21555
21557
21559
21561
21563
21565
21567

## Repeat Attacks 5
Unit No. | DATE | Status | Number of cars affected by graffiti/shadows on this unit | Total Number of Tags found | Total Tags Removed / Cleaned | Total Tags Not Cleaned on this Unit | Car Number (s) of Tags not cleaned (shadows) | Date of 2nd visit to clean remaining tags | Number of tags removed | Date of 3rd visit to clean remaining tags | Number of tags removed2 | Train Inspected and Fit for service (Y/N) | Inspected by Supervisor/Manager (Name) | Date of Completing all shadows (Tags) on this Unit excluding acid etched shadows | Car Number (s) of Tags not cleaned due to acid etched shadows
21302 | [15 empty] | Total Units Completed
21304 | [15 empty] | Total Trains | Total Units | Units Compled | % Completed
21306 | [15 empty] | 133 | 266 | 0 | 0
21308
21310
21312
21314
21316
21318
21320
21322
21326
21328
21330
21332
21334
21336
21338
21340
21342
21344
21346
21348
21350
21352
21354
21356
21358
21360
21362
21364
21366
21368
21370
21372
21374
21376
21378
21380
21382
21383
21386
21388
21390
21392
21394
21396
21398
21400
21402
21404
21406
21408
21410
21412
21414
21416
21418
21420
21422
21424
21426
21428
21430
21432
21434
21436
21438
21440
21442
21444
21446
21448
21450
21452
21454
21456
21458
21460
21462
21464
21466
21468
21470
21472
21474
21476
21478
21480
21482
21484
21486
21488
21490
21492
21494
21496
21498
21500
21502
21504
21506
21508
21510
21512
21514
21516
21518
21520
21522
21524
21526
21528
21530
21532
21534
21536
21538
21540
21542
21544
21546
21548
21550
21552
21554
21556
21558
21560
21562
21564
21566
21568
21301
21303
21305
21307
21309
21311
21313
21315
21317
21319
21321
21325
21327
21329
21331
21333
21335
21337
21339
21341
21343
21345
21347
21349
21351
21353
21355
21357
21359
21361
21363
21365
21367
21369
21371
21373
21375
21377
21379
21381
21384
21385
21387
21389
21391
21393
21395
21397
21399
21401
21403
21405
21407
21409
21411
21413
21415
21417
21419
21421
21423
21425
21427
21429
21431
21433
21435
21437
21439
21441
21443
21445
21447
21449
21451
21453
21455
21457
21459
21461
21463
21465
21467
21469
21471
21473
21475
21477
21479
21481
21483
21485
21487
21489
21491
21493
21495
21497
21499
21501
21503
21505
21507
21509
21511
21513
21515
21517
21519
21521
21523
21525
21527
21529
21531
21533
21535
21537
21539
21541
21543
21545
21547
21549
21551
21553
21555
21557
21559
21561
21563
21565
21567

## Repeat Attacks 6
Unit No. | DATE | Status | Number of cars affected by graffiti/shadows on this unit | Total Number of Tags found | Total Tags Removed / Cleaned | Total Tags Not Cleaned on this Unit | Car Number (s) of Tags not cleaned (shadows) | Date of 2nd visit to clean remaining tags | Number of tags removed | Date of 3rd visit to clean remaining tags | Number of tags removed2 | Train Inspected and Fit for service (Y/N) | Inspected by Supervisor/Manager (Name) | Date of Completing all shadows (Tags) on this Unit excluding acid etched shadows | Car Number (s) of Tags not cleaned due to acid etched shadows
21302 | [15 empty] | Total Units Completed
21304 | [15 empty] | Total Trains | Total Units | Units Compled | % Completed
21306 | [15 empty] | 133 | 266 | 0 | 0
21308
21310
21312
21314
21316
21318
21320
21322
21326
21328
21330
21332
21334
21336
21338
21340
21342
21344
21346
21348
21350
21352
21354
21356
21358
21360
21362
21364
21366
21368
21370
21372
21374
21376
21378
21380
21382
21383
21386
21388
21390
21392
21394
21396
21398
21400
21402
21404
21406
21408
21410
21412
21414
21416
21418
21420
21422
21424
21426
21428
21430
21432
21434
21436
21438
21440
21442
21444
21446
21448
21450
21452
21454
21456
21458
21460
21462
21464
21466
21468
21470
21472
21474
21476
21478
21480
21482
21484
21486
21488
21490
21492
21494
21496
21498
21500
21502
21504
21506
21508
21510
21512
21514
21516
21518
21520
21522
21524
21526
21528
21530
21532
21534
21536
21538
21540
21542
21544
21546
21548
21550
21552
21554
21556
21558
21560
21562
21564
21566
21568
21301
21303
21305
21307
21309
21311
21313
21315
21317
21319
21321
21325
21327
21329
21331
21333
21335
21337
21339
21341
21343
21345
21347
21349
21351
21353
21355
21357
21359
21361
21363
21365
21367
21369
21371
21373
21375
21377
21379
21381
21384
21385
21387
21389
21391
21393
21395
21397
21399
21401
21403
21405
21407
21409
21411
21413
21415
21417
21419
21421
21423
21425
21427
21429
21431
21433
21435
21437
21439
21441
21443
21445
21447
21449
21451
21453
21455
21457
21459
21461
21463
21465
21467
21469
21471
21473
21475
21477
21479
21481
21483
21485
21487
21489
21491
21493
21495
21497
21499
21501
21503
21505
21507
21509
21511
21513
21515
21517
21519
21521
21523
21525
21527
21529
21531
21533
21535
21537
21539
21541
21543
21545
21547
21549
21551
21553
21555
21557
21559
21561
21563
21565
21567

## Repeat Attacks 7
Unit No. | DATE | Status | Number of cars affected by graffiti/shadows on this unit | Total Number of Tags found | Total Tags Removed / Cleaned | Total Tags Not Cleaned on this Unit | Car Number (s) of Tags not cleaned (shadows) | Date of 2nd visit to clean remaining tags | Number of tags removed | Date of 3rd visit to clean remaining tags | Number of tags removed2 | Train Inspected and Fit for service (Y/N) | Inspected by Supervisor/Manager (Name) | Date of Completing all shadows (Tags) on this Unit excluding acid etched shadows | Car Number (s) of Tags not cleaned due to acid etched shadows
21302 | [15 empty] | Total Units Completed
21304 | [15 empty] | Total Trains | Total Units | Units Compled | % Completed
21306 | [15 empty] | 133 | 266 | 0 | 0
21308
21310
21312
21314
21316
21318
21320
21322
21326
21328
21330
21332
21334
21336
21338
21340
21342
21344
21346
21348
21350
21352
21354
21356
21358
21360
21362
21364
21366
21368
21370
21372
21374
21376
21378
21380
21382
21383
21386
21388
21390
21392
21394
21396
21398
21400
21402
21404
21406
21408
21410
21412
21414
21416
21418
21420
21422
21424
21426
21428
21430
21432
21434
21436
21438
21440
21442
21444
21446
21448
21450
21452
21454
21456
21458
21460
21462
21464
21466
21468
21470
21472
21474
21476
21478
21480
21482
21484
21486
21488
21490
21492
21494
21496
21498
21500
21502
21504
21506
21508
21510
21512
21514
21516
21518
21520
21522
21524
21526
21528
21530
21532
21534
21536
21538
21540
21542
21544
21546
21548
21550
21552
21554
21556
21558
21560
21562
21564
21566
21568
21301
21303
21305
21307
21309
21311
21313
21315
21317
21319
21321
21325
21327
21329
21331
21333
21335
21337
21339
21341
21343
21345
21347
21349
21351
21353
21355
21357
21359
21361
21363
21365
21367
21369
21371
21373
21375
21377
21379
21381
21384
21385
21387
21389
21391
21393
21395
21397
21399
21401
21403
21405
21407
21409
21411
21413
21415
21417
21419
21421
21423
21425
21427
21429
21431
21433
21435
21437
21439
21441
21443
21445
21447
21449
21451
21453
21455
21457
21459
21461
21463
21465
21467
21469
21471
21473
21475
21477
21479
21481
21483
21485
21487
21489
21491
21493
21495
21497
21499
21501
21503
21505
21507
21509
21511
21513
21515
21517
21519
21521
21523
21525
21527
21529
21531
21533
21535
21537
21539
21541
21543
21545
21547
21549
21551
21553
21555
21557
21559
21561
21563
21565
21567

## Repeat Attacks 8
Unit No. | DATE | Status | Number of cars affected by graffiti/shadows on this unit | Total Number of Tags found | Total Tags Removed / Cleaned | Total Tags Not Cleaned on this Unit | Car Number (s) of Tags not cleaned (shadows) | Date of 2nd visit to clean remaining tags | Number of tags removed | Date of 3rd visit to clean remaining tags | Number of tags removed2 | Train Inspected and Fit for service (Y/N) | Inspected by Supervisor/Manager (Name) | Date of Completing all shadows (Tags) on this Unit excluding acid etched shadows | Car Number (s) of Tags not cleaned due to acid etched shadows
21302 | [15 empty] | Total Units Completed
21304 | [15 empty] | Total Trains | Total Units | Units Compled | % Completed
21306 | [15 empty] | 133 | 266 | 0 | 0
21308
21310
21312
21314
21316
21318
21320
21322
21326
21328
21330
21332
21334
21336
21338
21340
21342
21344
21346
21348
21350
21352
21354
21356
21358
21360
21362
21364
21366
21368
21370
21372
21374
21376
21378
21380
21382
21383
21386
21388
21390
21392
21394
21396
21398
21400
21402
21404
21406
21408
21410
21412
21414
21416
21418
21420
21422
21424
21426
21428
21430
21432
21434
21436
21438
21440
21442
21444
21446
21448
21450
21452
21454
21456
21458
21460
21462
21464
21466
21468
21470
21472
21474
21476
21478
21480
21482
21484
21486
21488
21490
21492
21494
21496
21498
21500
21502
21504
21506
21508
21510
21512
21514
21516
21518
21520
21522
21524
21526
21528
21530
21532
21534
21536
21538
21540
21542
21544
21546
21548
21550
21552
21554
21556
21558
21560
21562
21564
21566
21568
21301
21303
21305
21307
21309
21311
21313
21315
21317
21319
21321
21325
21327
21329
21331
21333
21335
21337
21339
21341
21343
21345
21347
21349
21351
21353
21355
21357
21359
21361
21363
21365
21367
21369
21371
21373
21375
21377
21379
21381
21384
21385
21387
21389
21391
21393
21395
21397
21399
21401
21403
21405
21407
21409
21411
21413
21415
21417
21419
21421
21423
21425
21427
21429
21431
21433
21435
21437
21439
21441
21443
21445
21447
21449
21451
21453
21455
21457
21459
21461
21463
21465
21467
21469
21471
21473
21475
21477
21479
21481
21483
21485
21487
21489
21491
21493
21495
21497
21499
21501
21503
21505
21507
21509
21511
21513
21515
21517
21519
21521
21523
21525
21527
21529
21531
21533
21535
21537
21539
21541
21543
21545
21547
21549
21551
21553
21555
21557
21559
21561
21563
21565
21567

## Repeat Attacks 9
Unit No. | DATE | Status | Number of cars affected by graffiti/shadows on this unit | Total Number of Tags found | Total Tags Removed / Cleaned | Total Tags Not Cleaned on this Unit | Car Number (s) of Tags not cleaned (shadows) | Date of 2nd visit to clean remaining tags | Number of tags removed | Date of 3rd visit to clean remaining tags | Number of tags removed2 | Train Inspected and Fit for service (Y/N) | Inspected by Supervisor/Manager (Name) | Date of Completing all shadows (Tags) on this Unit excluding acid etched shadows | Car Number (s) of Tags not cleaned due to acid etched shadows
21302 | [15 empty] | Total Units Completed
21304 | [15 empty] | Total Trains | Total Units | Units Compled | % Completed
21306 | [15 empty] | 133 | 266 | 0 | 0
21308
21310
21312
21314
21316
21318
21320
21322
21326
21328
21330
21332
21334
21336
21338
21340
21342
21344
21346
21348
21350
21352
21354
21356
21358
21360
21362
21364
21366
21368
21370
21372
21374
21376
21378
21380
21382
21383
21386
21388
21390
21392
21394
21396
21398
21400
21402
21404
21406
21408
21410
21412
21414
21416
21418
21420
21422
21424
21426
21428
21430
21432
21434
21436
21438
21440
21442
21444
21446
21448
21450
21452
21454
21456
21458
21460
21462
21464
21466
21468
21470
21472
21474
21476
21478
21480
21482
21484
21486
21488
21490
21492
21494
21496
21498
21500
21502
21504
21506
21508
21510
21512
21514
21516
21518
21520
21522
21524
21526
21528
21530
21532
21534
21536
21538
21540
21542
21544
21546
21548
21550
21552
21554
21556
21558
21560
21562
21564
21566
21568
21301
21303
21305
21307
21309
21311
21313
21315
21317
21319
21321
21325
21327
21329
21331
21333
21335
21337
21339
21341
21343
21345
21347
21349
21351
21353
21355
21357
21359
21361
21363
21365
21367
21369
21371
21373
21375
21377
21379
21381
21384
21385
21387
21389
21391
21393
21395
21397
21399
21401
21403
21405
21407
21409
21411
21413
21415
21417
21419
21421
21423
21425
21427
21429
21431
21433
21435
21437
21439
21441
21443
21445
21447
21449
21451
21453
21455
21457
21459
21461
21463
21465
21467
21469
21471
21473
21475
21477
21479
21481
21483
21485
21487
21489
21491
21493
21495
21497
21499
21501
21503
21505
21507
21509
21511
21513
21515
21517
21519
21521
21523
21525
21527
21529
21531
21533
21535
21537
21539
21541
21543
21545
21547
21549
21551
21553
21555
21557
21559
21561
21563
21565
21567

## Repeat Attacks 10
Unit No. | DATE | Status | Number of cars affected by graffiti/shadows on this unit | Total Number of Tags found | Total Tags Removed / Cleaned | Total Tags Not Cleaned on this Unit | Car Number (s) of Tags not cleaned (shadows) | Date of 2nd visit to clean remaining tags | Number of tags removed | Date of 3rd visit to clean remaining tags | Number of tags removed2 | Train Inspected and Fit for service (Y/N) | Inspected by Supervisor/Manager (Name) | Date of Completing all shadows (Tags) on this Unit excluding acid etched shadows | Car Number (s) of Tags not cleaned due to acid etched shadows
21302 | [15 empty] | Total Units Completed
21304 | [15 empty] | Total Trains | Total Units | Units Compled | % Completed
21306 | [15 empty] | 133 | 266 | 0 | 0
21308
21310
21312
21314
21316
21318
21320
21322
21326
21328
21330
21332
21334
21336
21338
21340
21342
21344
21346
21348
21350
21352
21354
21356
21358
21360
21362
21364
21366
21368
21370
21372
21374
21376
21378
21380
21382
21383
21386
21388
21390
21392
21394
21396
21398
21400
21402
21404
21406
21408
21410
21412
21414
21416
21418
21420
21422
21424
21426
21428
21430
21432
21434
21436
21438
21440
21442
21444
21446
21448
21450
21452
21454
21456
21458
21460
21462
21464
21466
21468
21470
21472
21474
21476
21478
21480
21482
21484
21486
21488
21490
21492
21494
21496
21498
21500
21502
21504
21506
21508
21510
21512
21514
21516
21518
21520
21522
21524
21526
21528
21530
21532
21534
21536
21538
21540
21542
21544
21546
21548
21550
21552
21554
21556
21558
21560
21562
21564
21566
21568
21301
21303
21305
21307
21309
21311
21313
21315
21317
21319
21321
21325
21327
21329
21331
21333
21335
21337
21339
21341
21343
21345
21347
21349
21351
21353
21355
21357
21359
21361
21363
21365
21367
21369
21371
21373
21375
21377
21379
21381
21384
21385
21387
21389
21391
21393
21395
21397
21399
21401
21403
21405
21407
21409
21411
21413
21415
21417
21419
21421
21423
21425
21427
21429
21431
21433
21435
21437
21439
21441
21443
21445
21447
21449
21451
21453
21455
21457
21459
21461
21463
21465
21467
21469
21471
21473
21475
21477
21479
21481
21483
21485
21487
21489
21491
21493
21495
21497
21499
21501
21503
21505
21507
21509
21511
21513
21515
21517
21519
21521
21523
21525
21527
21529
21531
21533
21535
21537
21539
21541
21543
21545
21547
21549
21551
21553
21555
21557
21559
21561
21563
21565
21567

## Repeat Attacks 11
Unit No. | DATE | Status | Number of cars affected by graffiti/shadows on this unit | Total Number of Tags found | Total Tags Removed / Cleaned | Total Tags Not Cleaned on this Unit | Car Number (s) of Tags not cleaned (shadows) | Date of 2nd visit to clean remaining tags | Number of tags removed | Date of 3rd visit to clean remaining tags | Number of tags removed2 | Train Inspected and Fit for service (Y/N) | Inspected by Supervisor/Manager (Name) | Date of Completing all shadows (Tags) on this Unit excluding acid etched shadows | Car Number (s) of Tags not cleaned due to acid etched shadows
21302 | [15 empty] | Total Units Completed
21304 | [15 empty] | Total Trains | Total Units | Units Compled | % Completed
21306 | [15 empty] | 133 | 266 | 0 | 0
21308
21310
21312
21314
21316
21318
21320
21322
21326
21328
21330
21332
21334
21336
21338
21340
21342
21344
21346
21348
21350
21352
21354
21356
21358
21360
21362
21364
21366
21368
21370
21372
21374
21376
21378
21380
21382
21383
21386
21388
21390
21392
21394
21396
21398
21400
21402
21404
21406
21408
21410
21412
21414
21416
21418
21420
21422
21424
21426
21428
21430
21432
21434
21436
21438
21440
21442
21444
21446
21448
21450
21452
21454
21456
21458
21460
21462
21464
21466
21468
21470
21472
21474
21476
21478
21480
21482
21484
21486
21488
21490
21492
21494
21496
21498
21500
21502
21504
21506
21508
21510
21512
21514
21516
21518
21520
21522
21524
21526
21528
21530
21532
21534
21536
21538
21540
21542
21544
21546
21548
21550
21552
21554
21556
21558
21560
21562
21564
21566
21568
21301
21303
21305
21307
21309
21311
21313
21315
21317
21319
21321
21325
21327
21329
21331
21333
21335
21337
21339
21341
21343
21345
21347
21349
21351
21353
21355
21357
21359
21361
21363
21365
21367
21369
21371
21373
21375
21377
21379
21381
21384
21385
21387
21389
21391
21393
21395
21397
21399
21401
21403
21405
21407
21409
21411
21413
21415
21417
21419
21421
21423
21425
21427
21429
21431
21433
21435
21437
21439
21441
21443
21445
21447
21449
21451
21453
21455
21457
21459
21461
21463
21465
21467
21469
21471
21473
21475
21477
21479
21481
21483
21485
21487
21489
21491
21493
21495
21497
21499
21501
21503
21505
21507
21509
21511
21513
21515
21517
21519
21521
21523
21525
21527
21529
21531
21533
21535
21537
21539
21541
21543
21545
21547
21549
21551
21553
21555
21557
21559
21561
21563
21565
21567

## Repeat Attacks 12
Unit No. | DATE | Status | Number of cars affected by graffiti/shadows on this unit | Total Number of Tags found | Total Tags Removed / Cleaned | Total Tags Not Cleaned on this Unit | Car Number (s) of Tags not cleaned (shadows) | Date of 2nd visit to clean remaining tags | Number of tags removed | Date of 3rd visit to clean remaining tags | Number of tags removed2 | Train Inspected and Fit for service (Y/N) | Inspected by Supervisor/Manager (Name) | Date of Completing all shadows (Tags) on this Unit excluding acid etched shadows | Car Number (s) of Tags not cleaned due to acid etched shadows
21302 | [15 empty] | Total Units Completed
21304 | [15 empty] | Total Trains | Total Units | Units Compled | % Completed
21306 | [15 empty] | 133 | 266 | 0 | 0
21308
21310
21312
21314
21316
21318
21320
21322
21326
21328
21330
21332
21334
21336
21338
21340
21342
21344
21346
21348
21350
21352
21354
21356
21358
21360
21362
21364
21366
21368
21370
21372
21374
21376
21378
21380
21382
21383
21386
21388
21390
21392
21394
21396
21398
21400
21402
21404
21406
21408
21410
21412
21414
21416
21418
21420
21422
21424
21426
21428
21430
21432
21434
21436
21438
21440
21442
21444
21446
21448
21450
21452
21454
21456
21458
21460
21462
21464
21466
21468
21470
21472
21474
21476
21478
21480
21482
21484
21486
21488
21490
21492
21494
21496
21498
21500
21502
21504
21506
21508
21510
21512
21514
21516
21518
21520
21522
21524
21526
21528
21530
21532
21534
21536
21538
21540
21542
21544
21546
21548
21550
21552
21554
21556
21558
21560
21562
21564
21566
21568
21301
21303
21305
21307
21309
21311
21313
21315
21317
21319
21321
21325
21327
21329
21331
21333
21335
21337
21339
21341
21343
21345
21347
21349
21351
21353
21355
21357
21359
21361
21363
21365
21367
21369
21371
21373
21375
21377
21379
21381
21384
21385
21387
21389
21391
21393
21395
21397
21399
21401
21403
21405
21407
21409
21411
21413
21415
21417
21419
21421
21423
21425
21427
21429
21431
21433
21435
21437
21439
21441
21443
21445
21447
21449
21451
21453
21455
21457
21459
21461
21463
21465
21467
21469
21471
21473
21475
21477
21479
21481
21483
21485
21487
21489
21491
21493
21495
21497
21499
21501
21503
21505
21507
21509
21511
21513
21515
21517
21519
21521
21523
21525
21527
21529
21531
21533
21535
21537
21539
21541
21543
21545
21547
21549
21551
21553
21555
21557
21559
21561
21563
21565
21567