## Bakeloo Line
Unit No. | DATE | Status | Number of cars affected by graffiti/shadows on this unit | Total Number of Tags found | Total Tags Removed / Cleaned | Total Tags Not Cleaned on this Unit | Car Number (s) of Tags not cleaned (shadows) | Date of 2nd visit to clean remaining tags | Number of tags removed | Date of 3rd visit to clean remaining tags | Number of tags removed2 | Train Inspected and Fit for service (Y/N) | Inspected by Supervisor/Manager (Name) | Date of Completing all shadows (Tags) on this Unit excluding acid etched shadows | Car Number (s) of Tags not cleaned due to acid etched shadows
3231 | 2025-05-15 |  | 4 | 152 | 152 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-05-15 | 3231 | Total Units Completed
3232 | 2025-06-05 |  | 4 | 224 | 179 | 65 | 2 | 2025-06-30 | 30 |  |  | Y | Daniela | 2025-06-30 |  | Total Trains | Total Units | Units Completed | % Completed
3233 | 2025-06-04 | Stopped | 4 | 139 | 43 | 96 | 3 | 2025-06-15 | 47 |  |  | Y | Daniela | 2025-06-15 | 3233 | 36 | 72 | 65 | 90.28%
3234 | 2025-06-10 |  | 4 | 311 | 254 | 57 | 1 | 2025-07-01 | 59 |  |  | Y | Daniela | 2025-06-18 | 3234
3235 | 2025-06-18 |  | 4 | 340 | 340 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-06-18 | 3235
3236 | 2025-05-29 |  | 4 | 175 | 175 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-05-29 | 3236
3237 | 2025-04-27 |  | 4 | 155 | 20 | 135 | 3 | 2025-05-08 | 70 | 2025-05-26 | 65 | Y | Daniela | 2025-05-26 | 3237
3238 | 2025-05-14 |  | 4 | 89 | 77 | 12 | 3 | 2025-06-17 | 165 |  |  | Y | Daniela | 2025-06-17 | 4338
3239 | 2025-06-22 |  | 4 | 435 | 435 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-06-22 | 3239
3240 | 2025-06-13 |  | 4 | 301 | 301 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-06-13 | 3240
3241 | 2025-04-24 |  | 4 | 205 | 90 | 115 | 3 | 2025-05-28 | 115 |  |  | Y | Daniela | 2025-05-28 | 3241
3242 | 2025-04-17 |  | 4 | 360 | 360 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-04-17 | 3242
3243 | 2025-05-20 |  | 4 | 384 | 384 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-05-20 | 3243
3244 | 2025-04-29 |  | 1 | 213 | 63 | 150 | 0 | 2025-06-30 | 105 |  |  | Y | Daniela | 2025-06-01 | 3244
3245 | 2025-04-29 | Stopped | 4 | 105 | 105 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-04-29 | 3245
3246 | 2025-05-04 |  | 4 | 177 | 14 | 163 | 3 | 2025-06-25 | 163 |  |  | Y | Daniela | 2025-06-25 | 3346
3247 |  |  | 4 | 0 | 0 | 0 | 0
3248 | 2025-06-26 |  | 4 | 272 | 272 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-07-04 | 3248
3250 | 2025-05-06 |  | 4 | 247 | 205 | 42 | 2 | 2025-06-20 | 145 |  |  | Y | Daniela | 2025-06-20 | 3250
3251 | 2025-05-01 |  | 4 | 163 | 113 | 50 | 2 | 2025-06-11 | 115 |  |  | Y | Daniela | 2025-06-11 | 3251
3252 | 2025-06-08 | Stopped | 4 | 341 | 284 | 57 | 1 | 2025-06-11 | 42 | 2025-06-11 | 104 | Y | Daniela | 2025-06-11 | 3352
3253 |  |  | 4 | 0 | 0 | 0 | 0
3254 | 2025-06-12 |  | 4 | 488 | 488 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-06-12 | 3254
3255 | 2025-05-18 |  | 4 | 372 | 352 | 0 | 1 | 2025-05-18 | 105 | 2025-06-16 | 52 | Y | Daniela | 2025-06-16 | 3255
3256 | 2025-06-26 | Stopped | 4 | 324 | 144 | 180 | 2 | 2025-07-03 | 87 | 2025-07-04 | 93 | Y | Daniela | 2025-07-04 | 3256
3258 | 2025-05-26 |  | 4 | 190 | 190 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-05-26 | 3258
3259 | 2025-06-19 |  | 4 | 458 | 458 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-06-19 | 3259
3260 |  |  | 4 | 0 | 0 | 0 | 0
3261 | 2025-05-19 |  | 4 | 195 | 195 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-05-19 | 3261
3262 | 2025-04-14 |  | 4 | 116 | 116 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-04-14
3263 | 2025-04-15 |  | 4 | 59 | 59 | 0 | 2 | 2025-06-20 | 42 | 2025-06-25 | 39 | Y | Daniela | 2025-06-25 | 3263
3264 | 2025-05-07 |  | 4 | 201 | 201 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-05-07 | 3264
3265 | 2025-06-15 |  | 4 | 430 | 359 | 71 | 0 |  |  |  |  | Y | Daniela | 2025-06-15 | 3265
3266 | 2025-05-01 |  | 4 | 167 | 167 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-05-01 | 3266
3267 | 2025-04-29 | Stopped | 3 | 177 | 173 | 4 | 1 |  |  |  |  | Y | Daniela
3299 | 2025-05-11 |  | 4 | 123 | 123 | 0 | 2 | 2025-06-12 | 35 |  |  | Y | Daniela | 2025-06-12 | 3299
3531 | 2025-05-13 |  | 3 | 146 | 105 | 41 | 2 | 2025-06-24 | 473 |  |  | Y | Daniela | 2025-06-24 | 3431
3532 |  |  | 3 | 0 | 0 | 0 | 0
3533 |  |  | 3 | 0 | 0 | 0 | 0
3534 | 2025-07-02 | Stopped | 3 | 0 | 0 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-07-02
3535 | 2025-06-26 |  | 2 | 158 | 158 | 0 | 1 | 2025-07-01 | 40 |  |  | Y | Daniela | 2025-06-26 | 3535
3536 | 2025-05-27 | Stopped | 3 | 276 | 276 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-05-27 | 3536
3537 | 2025-06-02 |  | 3 | 188 | 95 | 93 | 2 | 2025-06-16 | 144 |  |  | Y | Daniela | 2025-06-16 | 3437
3538 | 2025-04-30 |  | 3 | 265 | 195 | 70 | 1 | 2025-07-02 | 55 |  |  | Y | Daniela | 2025-04-30 | 3538
3540 | 2025-04-22 | Stopped | 3 | 30 | 30 | 0 | 2 | 2025-07-06 | 162 |  |  | Y | Daniela | 2025-07-06 | 3540
3541 | 2025-04-27 |  | 3 | 356 | 356 | 0 | 0 |  |  |  |  | Y | Daniela | 27.04.2025 | 3541
3542 | 2025-04-17 |  | 3 | 283 | 283 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-04-17 | 3542
3543 | 13/04/2025 |  | 3 | 61 | 61 | 13 | 2 | 2025-06-04 | 13 |  |  | Y | Daniela | 04/06/2025 | 3543
3544 | 2025-04-22 | Stopped | 3 | 265 | 220 | 45 | 1 | 2025-06-09 | 97 | 2025-06-11 | 12 | Y | Daniela | 2025-06-11 | 3544
3545 | 2025-05-06 |  | 3 | 141 | 141 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-05-06 | 3545
3546 | 2025-06-04 |  | 3 | 235 | 95 | 140 | 2 | 2025-06-19 | 240 |  |  | Y | Daniela | 2025-06-04 | 3546
3547 | 2025-05-05 |  | 3 | 315 | 315 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-05-05 | 3547
3548 | 2025-04-21 |  | 3 | 276 | 276 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-04-21 | 3548
3549 | 2025-04-24 |  | 3 | 210 | 135 | 75 | 2 | 2025-05-17 | 61 | 2025-06-30 | 115 | Y | Daniela | 2025-05-17 | 3549
3550 | 2025-06-11 |  | 3 | 466 | 398 | 68 | 2 | 2025-07-04 | 48 |  |  | Y | Daniela | 2025-06-11 | 3550
3551 | 2025-05-22 | Stopped | 3 | 192 | 192 | 0 | 1 |  |  |  |  | Y | Daniela |  | 3551
3552 | 2025-06-16 |  | 3 | 422 | 386 | 36 | 2 | 2025-07-18 | 48 |  |  | Y | Daniela | 2025-07-18 | 3552
3553 | 2025-04-15 |  | 3 | 281 | 122 | 159 | 2 | 2025-06-27 | 351 |  |  | Y | Daniela | 2025-06-27 | 3553
3554 | 2025-05-04 | Stopped | 3 | 219 | 219 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-05-04 | 3554
3555 | 2025-06-17 |  | 3 | 352 | 352 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-05-04 | 3555
3556 | 2025-06-15 |  | 1 | 13 | 0 | 0 | 1 | 2025-07-10 | 8 |  |  | Y | Daniela | 2025-06-15 | 3556
3557 | 13/04/2025 |  | 3 | 97 | 97 | 0 | 0 |  |  |  |  | Y | Daniela | 13/04/2025 | 3557
3558 | 2025-04-16 |  | 3 | 302 | 145 | 157 | 2 | 2025-06-22 | 116 | 2025-06-23 | 226 | Y | Daniela | 2025-06-23 | 3558
3559 | 2025-04-14 |  | 3 | 202 | 108 | 94 | 1 | 2025-06-15 | 97 |  |  | Y | Daniela | 15.06.2025 | 3559
3560 | 2025-05-21 |  | 3 | 237 | 237 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-05-21 | 3560
3561 | 2025-05-15 |  | 3 | 267 | 95 | 172 | 2 | 2025-06-01 | 172 |  |  | Y | Daniela | 2025-06-01 | 3561
3562 | 2025-04-28 | Stopped | 3 | 190 | 140 | 50 | 1 | 2025-06-18 | 59 |  |  | Y | Daniela | 2025-06-18 | 3562
3563 | 2025-05-29 |  | 3 | 14 | 14 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-05-29 | 3563
3564 | 2025-05-25 |  | 3 | 212 | 212 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-05-25 | 3564
3565 | 2025-05-13 |  | 3 | 234 | 234 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-05-13 | 3565
3566 | 2025-06-13 |  | 3 | 339 | 339 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-06-13 | 3566
3567 | 2025-05-11 |  | 3 | 136 | 98 | 38 | 2 | 2025-06-10 | 214 |  |  | Y | Daniela | 2025-06-10 | 3567
Key
Stopped Units

## Repeat Attacks 1
Unit No. | DATE | Status | Number of cars affected by graffiti/shadows on this unit | Total Number of Tags found | Total Tags Removed / Cleaned | Total Tags Not Cleaned on this Unit | Car Number (s) of Tags not cleaned (shadows) | Date of 2nd visit to clean remaining tags | Number of tags removed | Date of 3rd visit to clean remaining tags | Number of tags removed2 | Train Inspected and Fit for service (Y/N) | Inspected by Supervisor/Manager (Name) | Date of Completing all shadows (Tags) on this Unit excluding acid etched shadows | Car Number (s) of Tags not cleaned due to acid etched shadows
3231 | 2025-06-17 |  | 4 | 113 | 113 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-06-17 | 3231 | Total Units Completed
3232 | 2025-07-12 |  | 1 | 20 | 20 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-07-12 |  | Total Trains | Total Units | Units Compled | % Completed
3233 | 2025-06-26 |  | 2 | 33 | 33 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-06-26 | 3233 | 36 | 72 | 57 | 79.17%
3234 | 2025-07-01 |  | 3 | 91 | 91 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-07-01
3235
3236 | 2025-06-29 |  | 3 | 80 | 80 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-06-29 | 3236
3237 | 2025-05-26 |  | 3 | 52 | 52 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-05-26 | 3237
3238 | 2025-06-17 |  | 1 | 15 | 15 | 0 | 3 | 2025-06-25 | 51 |  |  | Y | Daniela | 2025-06-25 | 3238
3239
3240 | 2025-06-24 |  | 1 | 28 | 28 | 0 | 3 | 2025-07-13 | 95 |  |  | Y | Daniela | 2025-06-24 | 3240
3241 | 2025-05-28 |  | 1 | 30 | 30 | 0 | 0 | 2025-06-23 | 12 | 2025-06-26 | 5 | Y | Daniela | 2025-06-26 | 3341
3242 | 2025-06-03 |  | 4 | 190 | 190 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-06-03 | 3224
3243 | 2025-06-16 |  | 3 | 117 | 117 | 0 | 1 | 2025-07-08 | 2 |  |  | Y | Daniela | 2025-06-16
3244 | 2025-06-01 |  | 3 | 46 | 46 | 0 | 0 | 2025-06-30 | 57 |  |  | Y | Daniela | 2025-06-01 | 3244
3245
3246 | 2025-06-25 |  | 3 | 100 | 100 | 0 | 1 | 2025-07-02 | 24 |  |  | Y | Daniela | 2025-06-25 | 3246
3247
3248 | 2025-07-17 |  | 1 | 6 | 6 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-07-17 | 3248
3250 | 2025-06-20 |  | 2 | 259 | 259 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-06-20
3251 | 2025-06-11 |  | 1 | 18 | 18 | 0 | 0 | 2025-06-23 | 92 |  |  | Y | Daniela | 2025-06-23 | 3251
3252
3253
3254
3255 | 2025-06-16 |  | 3 | 86 | 86 | 0 | 1 |  |  |  |  | Y | Daniela | 2025-06-16 | 3255
3256
3258 | 2025-06-15 |  | 4 | 37 | 37 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-06-15
3259 | 2025-06-23 |  | 2 | 30 | 30 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-06-23
3260
3261 | 2025-06-26 |  | 1 | 34 | 34 | 0 | 3 | 2025-07-02 | 174 |  |  | Y | Daniela | 2025-07-02 | 3261
3262 | 2025-06-11 |  | 4 | 86 | 33 | 53 | 0 |  |  |  |  | Y | Daniela | 2025-06-11 | 3262
3263 | 2025-06-25 |  | 3 | 196 | 196 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-06-25 | 3263
3264 | 2025-06-18 |  | 4 | 121 | 121 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-06-18
3265 | 2025-06-26 |  | 4 | 100 | 100 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-04-26
3266 | 2025-06-05 |  | 4 | 92 | 92 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-06-05
3267
3299 | 2025-06-12 |  | 2 | 50 | 50 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-06-12
3531 | 2025-06-24 |  | 1 | 86 | 86 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-06-24 | 3531
3532 |  |  | 3 | 0 | 0 | 0
3533 |  |  | 3 | 0 | 0 | 0
3534 |  |  | 3 | 0 | 0 | 0
3535 | 2025-07-01 |  | 1 | 45 | 45 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-07-01 | 3535
3536 | 2025-06-23 |  | 1 | 3 | 3 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-06-23 | 3536
3537 | 2025-07-06 |  | 3 | 59 | 59 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-07-06 | 3537
3538 | 2025-07-02 |  | 2 | 195 | 147 | 48 | 1 | 2025-07-09 | 48 |  |  | Y | Daniela | 2025-07-02
3540
3541 | 2025-06-21 |  | 3 | 271 | 271 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-06-21 | 3541
3542 | 2025-05-08 |  | 3 | 120 | 120 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-05-08 | 3542
3543 | 2025-06-16 |  | 3 | 117 | 177 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-06-16
3544 | 2025-06-09 | Stopped | 2 | 142 | 130 | 12 | 0 |  |  |  |  | Y | Daniela | 2025-06-09 | 3544
3545 | 2025-06-15 |  | 3 | 108 | 108 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-06-15 | 3545
3546
3547 | 2025-06-22 |  | 3 | 99 | 99 | 20 | 1 | 2025-06-30 | 44 |  |  | Y | Daniela | 2025-06-30 | 3547
3548 | 2025-06-25 |  | 3 | 126 | 126 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-06-25 | 3548
3549 | 2025-06-10 |  | 2 | 285 | 277 | 8 | 1 | 2025-07-20 | 12 |  |  | Y | Daniela | 2025-07-20 | 3549
3550 | 2025-07-04 |  | 1 | 8 | 8 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-07-04
3551 | 2025-06-23 | Stopped | 3 | 92 | 47 | 25 | 0 |  |  |  |  | Y | Daniela | 2025-06-23 | 3551
3552 | 2025-07-18 |  | 1 | 49 | 49 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-07-18 | 3552
3553 | 2025-06-27 |  | 1 | 104 | 104 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-06-27 | 3553
3554 | 2025-06-02 | Stopped | 3 | 108 | 108 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-06-02 | 3554
3555 | 2025-06-24 |  | 2 | 16 | 16 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-06-24 | 3555
3556 | 2025-07-10 |  | 1 | 81 | 81 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-07-10
3557 | 2025-06-11 |  | 3 | 362 | 362 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-06-11 | 3557
3558 | 2025-06-23 |  | 1 | 114 | 114 | 0 | 2 | 2025-07-02 | 68 |  |  | Y | Daniela | 2025-06-23 | 3558
3559 | 2025-06-15 |  | 2 | 67 | 67 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-06-15 | 3559
3560 | 2025-06-30 |  | 3 | 277 | 277 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-06-30 | 3560
3561 | 2025-06-01 |  | 3 | 57 | 10 | 47 | 2 | 2025-06-25 | 47 |  |  | Y | Daniela | 2025-06-25 | 3561
3562 | 2025-06-18 | Stopped | 2 | 253 | 253 | 0 | 0 | 2025-07-13 | 32 |  |  | Y | Daniela | 2025-06-18 | 3562
3563 | 2025-06-29 |  | 2 | 75 | 75 | 0 | 1 | 2025-07-09 | 5 |  |  | Y | Daniela | 2025-06-29 | 3563
3564 | 2025-06-19 |  | 2 | 127 | 127 | 0 | 1 | 2025-07-06 | 3 |  |  | Y | Daniela | 2025-06-19 | 3564
3565 | 2025-06-25 |  | 3 | 63 | 23 | 40 | 1 | 2025-06-29 | 59 |  |  | Y | Daniela | 2025-06-29 | 3565
3566 | 2025-06-16 |  | 3 | 94 | 94 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-06-16 | 3565
3567 | 2025-06-10 |  | 1 | 32 | 32 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-06-10 | 3567

## Repeat Attacks 2
Unit No. | DATE | Status | Number of cars affected by graffiti/shadows on this unit | Total Number of Tags found | Total Tags Removed / Cleaned | Total Tags Not Cleaned on this Unit | Car Number (s) of Tags not cleaned (shadows) | Date of 2nd visit to clean remaining tags | Number of tags removed | Date of 3rd visit to clean remaining tags | Number of tags removed2 | Train Inspected and Fit for service (Y/N) | Inspected by Supervisor/Manager (Name) | Date of Completing all shadows (Tags) on this Unit excluding acid etched shadows | Car Number (s) of Tags not cleaned due to acid etched shadows
3231 | 2025-07-16 |  | 4 | 99 | 55 | 44 | 3 |  |  |  |  | Y | Daniela |  |  | Total Units Completed
3232 | 2025-07-20 |  | 4 | 52 | 48 | 4 | 1 | 2025-07-21 | 4 |  |  | Y | Daniela | 2025-07-21 | 3232 | Total Trains | Total Units | Units Compled | % Completed
3233 | [15 empty] | 36 | 72 | 34 | 47.22%
3234 | 2025-07-20 |  | 1 | 4 | 4 | 0 | 0 |  |  |  |  | Y | Daniela | 20/07/205 | 3234
3235
3236
3237 | 2025-07-06 |  | 4 | 98 | 98 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-07-06 | 3237
3238 | 2025-06-26 |  | 2 | 14 | 14 | 0 | 1 | 2025-07-05 | 14 |  |  | Y | Daniela | 2025-07-05 | 3238
3239
3240 | 2025-07-13 |  | 1 | 27 | 27 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-07-13
3241 | 2025-06-23 |  | 3 | 12 | 12 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-06-23 | 3241
3242 | 2025-06-25 |  | 4 | 58 | 58 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-06-25 | 3242
3243 | 2025-07-08 |  | 3 | 16 | 16 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-07-08 | 3243
3244 | 2025-06-30 |  | 1 | 27 | 27 | 0 | 3 | 2025-07-13 | 192 |  |  | Y | Daniela | 2025-07-13 | 3244
3245
3246
3247
3248
3250
3251
3252
3253
3254
3255
3256
3258 | 2025-07-06 |  | 1 | 5 | 5 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-07-06
3259
3260
3261 | 2025-07-09 |  | 2 | 17 | 17 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-07-09
3262 | 2025-06-24 |  | 4 | 160 | 160 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-06-24
3263 | 2025-07-08 |  | 1 | 12 | 12 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-07-08
3264 | 2025-06-05 |  | 1 | 26 | 26 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-06-05
3265
3266 | 2025-06-15 |  | 2 | 22 | 22 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-06-15
3267
3299
3531 | 2025-07-19 |  | 3 | 59 | 59 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-07-19 | 3531
3532
3533
3534
3535
3536
3537 | 2025-07-12 |  | 1 | 9 | 9 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-07-12
3538 | 2025-07-09 |  | 1 | 8 | 8 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-07-09
3540
3541 | 2025-07-10 |  | 3 | 166 | 166 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-07-10 | 3541
3542 | 2025-06-20 |  | 3 | 198 | 198 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-06-20 | 3542
3543
3544
3545
3546
3547 | 2025-06-30 |  | 3 | 57 | 40 | 17 | 2 | 2025-07-12 | 17 |  |  | Y | Daniela | 2025-06-30 | 3547
3548 | 2025-07-02 |  | 1 | 24 | 24 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-07-02
3549 | 2025-06-30 |  | 2 | 112 | 60 | 52 | 1 | 2025-07-01 | 52 |  |  | Y | Daniela | 2025-07-01 | 3549
3550
3551
3552
3553 | 2025-07-04 |  | 1 | 33 | 33 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-07-04 | 3553
3554
3555
3556
3557 | 2025-06-24 |  | 3 | 112 | 112 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-06-24 | 3557
3558 | 2025-07-08 |  | 3 | 65 | 65 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-07-08
3559 | 2025-06-26 |  | 3 | 13 | 13 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-06-26 | 3559
3560 | 2025-07-11 |  | 3 | 149 | 63 | 86 | 2 | 2025-07-13 | 74 | 2025-07-14 | 18 | Y | Daniela | 2025-07-14 | 3560
3561 | 2025-06-25 |  | 3 | 94 | 94 | 28 | 1 | 2025-07-04 | 28 |  |  | Y | Daniela | 2025-07-04 | 3561
3562 | 2025-07-13 |  | 2 | 77 | 77 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-07-13 | 3562
3563
3564 | 2025-06-23 |  | 1 | 22 | 22 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-06-23 | 3564
3565 | 2025-07-08 |  | 2 | 47 | 47 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-07-08
3566 | 2025-06-24 |  | 1 | 17 | 17 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-06-24
3567 | 2025-06-23 |  | 1 | 29 | 29 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-06-23 | 3567

## Repeat Attacks 3
Unit No. | DATE | Status | Number of cars affected by graffiti/shadows on this unit | Total Number of Tags found | Total Tags Removed / Cleaned | Total Tags Not Cleaned on this Unit | Car Number (s) of Tags not cleaned (shadows) | Date of 2nd visit to clean remaining tags | Number of tags removed | Date of 3rd visit to clean remaining tags | Number of tags removed2 | Train Inspected and Fit for service (Y/N) | Inspected by Supervisor/Manager (Name) | Date of Completing all shadows (Tags) on this Unit excluding acid etched shadows | Car Number (s) of Tags not cleaned due to acid etched shadows
3231 | [15 empty] | Total Units Completed
3232 | 2025-07-21 |  | 1 | 4 | 4 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-07-21 | 3232 | Total Trains | Total Units | Units Compled | % Completed
3233 | [15 empty] | 36 | 72 | 17 | 23.61%
3234
3235
3236
3237
3238 | 2025-07-15 |  | 2 | 23 | 23 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-07-15 | 3238
3239
3240
3241
3242
3243 | 2025-07-18 |  | 3 | 20 | 20 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-07-18 | 3243
3244
3245
3246
3247
3248
3250
3251
3252
3253
3254
3255
3256
3258 | 2025-07-20 |  | 1 | 12 | 12 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-07-20 | 3258
3259
3260
3261
3262 | 2025-07-19 |  | 3 | 14 | 9 | 5 | 1 |  |  |  |  | Y | Daniela | 2025-07-19 | 3262
3263
3264
3265
3266 | 2025-07-21 |  | 2 | 24 | 24 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-07-21 | 3266
3267
3299
3531
3532
3533
3534
3535
3536
3537 | 2025-07-20 |  | 1 | 9 | 9 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-07-20 | 3537
3538
3540
3541
3542 | 2025-06-26 |  | 3 | 193 | 193 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-06-26 | 3542
3543
3544
3545
3546
3547 | 2025-07-21 |  | 1 | 16 | 16 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-07-21 | 3547
3548 | 2025-07-21 |  | 2 | 41 | 41 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-07-21 | 3548
3549 | 2025-07-20 |  | 2 | 97 | 97 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-07-20 | 3549
3550
3551
3552
3553 | 2025-07-15 |  | 1 | 35 | 35 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-07-15 | 3553
3554
3555
3556
3557 | 2025-07-01 |  | 1 | 16 | 16 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-07-01 | 3557
3558
3559 | 2025-07-06 |  | 2 | 63 | 20 | 0 | 1 | 2025-07-08 | 20 |  |  | Y | Daniela | 2025-07-08 | 3559
3560
3561 | 2025-07-04 |  | 2 | 11 | 11 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-07-04 | 3561
3562
3563
3564 | 2025-06-28 |  | 2 | 15 | 15 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-06-28 | 3564
3565 | 2025-07-14 |  | 2 | 23 | 23 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-07-14 | 3565
3566
3567

## Repeat Attacks 4
Unit No. | DATE | Status | Number of cars affected by graffiti/shadows on this unit | Total Number of Tags found | Total Tags Removed / Cleaned | Total Tags Not Cleaned on this Unit | Car Number (s) of Tags not cleaned (shadows) | Date of 2nd visit to clean remaining tags | Number of tags removed | Date of 3rd visit to clean remaining tags | Number of tags removed2 | Train Inspected and Fit for service (Y/N) | Inspected by Supervisor/Manager (Name) | Date of Completing all shadows (Tags) on this Unit excluding acid etched shadows | Car Number (s) of Tags not cleaned due to acid etched shadows
3231 | [15 empty] | Total Units Completed
3232 | [15 empty] | Total Trains | Total Units | Units Compled | % Completed
3233 | [15 empty] | 36 | 72 | 3 | 0.041667
3234
3235
3236
3237
3238
3239
3240
3241
3242
3243
3244
3245
3246
3247
3248
3250
3251
3252
3253
3254
3255
3256
3258
3259
3260
3261
3262
3263
3264
3265
3266
3267
3299
3531
3532
3533
3534
3535
3536
3537
3538
3540
3541
3542 | 2025-07-16 |  | 3 | 74 | 74 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-07-16 | 3542
3543
3544
3545
3546
3547
3548
3549
3550
3551
3552
3553
3554
3555
3556
3557 | 2025-07-16 |  | 3 | 38 | 38 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-07-16 | 3557
3558
3559
3560
3561 | 2025-07-17 |  | 2 | 50 | 50 | 0 | 0 |  |  |  |  | Y | Daniela | 2025-07-17 | 3561
3562
3563
3564
3565
3566
3567

## Repeat Attacks 5
Unit No. | DATE | Status | Number of cars affected by graffiti/shadows on this unit | Total Number of Tags found | Total Tags Removed / Cleaned | Total Tags Not Cleaned on this Unit | Car Number (s) of Tags not cleaned (shadows) | Date of 2nd visit to clean remaining tags | Number of tags removed | Date of 3rd visit to clean remaining tags | Number of tags removed2 | Train Inspected and Fit for service (Y/N) | Inspected by Supervisor/Manager (Name) | Date of Completing all shadows (Tags) on this Unit excluding acid etched shadows | Car Number (s) of Tags not cleaned due to acid etched shadows
3231 | [15 empty] | Total Units Completed
3232 | [15 empty] | Total Trains | Total Units | Units Compled | % Completed
3233 | [15 empty] | 36 | 72 | 0 | 0
3234
3235
3236
3237
3238
3239
3240
3241
3242
3243
3244
3245
3246
3247
3248
3250
3251
3252
3253
3254
3255
3256
3258
3259
3260
3261
3262
3263
3264
3265
3266
3267
3299
3531
3532
3533
3534
3535
3536
3537
3538
3540
3541
3542
3543
3544
3545
3546
3547
3548
3549
3550
3551
3552
3553
3554
3555
3556
3557
3558
3559
3560
3561
3562
3563
3564
3565
3566
3567

## Repeat Attacks 6
Unit No. | DATE | Status | Number of cars affected by graffiti/shadows on this unit | Total Number of Tags found | Total Tags Removed / Cleaned | Total Tags Not Cleaned on this Unit | Car Number (s) of Tags not cleaned (shadows) | Date of 2nd visit to clean remaining tags | Number of tags removed | Date of 3rd visit to clean remaining tags | Number of tags removed2 | Train Inspected and Fit for service (Y/N) | Inspected by Supervisor/Manager (Name) | Date of Completing all shadows (Tags) on this Unit excluding acid etched shadows | Car Number (s) of Tags not cleaned due to acid etched shadows
3231 | [15 empty] | Total Units Completed
3232 | [15 empty] | Total Trains | Total Units | Units Compled | % Completed
3233 | [15 empty] | 36 | 72 | 0 | 0
3234
3235
3236
3237
3238
3239
3240
3241
3242
3243
3244
3245
3246
3247
3248
3250
3251
3252
3253
3254
3255
3256
3258
3259
3260
3261
3262
3263
3264
3265
3266
3267
3299
3531
3532
3533
3534
3535
3536
3537
3538
3540
3541
3542
3543
3544
3545
3546
3547
3548
3549
3550
3551
3552
3553
3554
3555
3556
3557
3558
3559
3560
3561
3562
3563
3564
3565
3566
3567